## ACCESS enrollment
ANNUAL IMPLEMENTATION PLAN 2018
ACCESS: | Priority Improvement Areas (PIAs)
(ENROLMENT)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Enrolment | Increase enrolment from 1040 to 1,200 from Grade 7 to Grade 10 in 2019 | 50 or 3% | Communicating project team and parents | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Conducting Oplan - Balik Eskwela campaign | Teachers, School Head, stakeholders | With in the Municipality of Merida | 1000
|  |  | Identifying intervention programs to fit the need of the learner | Teachers, School Head, stakeholders, Project BEST Coordinator | MVS | NC
|  |  | Monitoring of Students attendance | Teachers Adviser | MVS | NC
|  |  | Intensifying "Project BEST " | Project BEST Coordinator | MVS | NC
|  |  | Giving of awards to "Balik- Eskwela" highest achievers and advisers | Teachers, School Head, stakeholders, Project BEST Coordinator | MVS | 2000 | MOOE
|  |  | Acomplishing the ACR |  | MVS | NC

## talento pagagk sardo pag arts
ANNUAL IMPLEMENTATION PLAN 2018
ACCESS: | Priority Improvement Areas (PIAs)
School-Based Adopt-A-Student Program
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Talento MO- Pag-agak KO | Procure 10 sets of costumes for MVS PAG Organization in 2019 | 2 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing PAG to develop singing, dancing, and acting skills of students | MAPEH Teachers | MVS | 5000 | Club Funds/Personal Donations
|  |  | Assigning MAPEH teacher to handle the group |  | MVS | 5000 | PTA
|  |  | Purchasing materials for costume production | MAPEH Teachers, supply officers | MVS | 10000 | PTA
|  |  | Participating during monthly culmination | MAPEH Teachers and students | MVS | 1000 | MOOE
|  |  | Implementing annual cultural production in the school (PAG Recital) | MAPEH Teachers and PAG Members/ students
|  |  | Conducting Fund raising activities through PAG Recital Show for the Club to support the Adopt-a-student- program | DORP Team, MAPEH Teachers and PAG Members/ students |  | 5000 | Club Funds/Personal Donations
|  |  | Liquadating the expenses | MAPEH Teachers and PAG Members/ students |  | NC
|  |  | Accomplishing the ACR | Project Chairman |  | NC

## ACCESS sakay na
ANNUAL IMPLEMENTATION PLAN 2018
ACCESS: | Priority Improvement Areas (PIAs)
(DORP)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
SAKAY NA- LIBRE PA | Save 92 SARDO students to sustain zero- drop out by 2019 | 31 | Communicating project team and parents | Teacher- Adviser, Guidance Counselor, stakeholders, School Principal, Project BEST coordinator | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Identifying SARDO students |  | MVS | NC
|  |  | Preparing of Program design to answer SARDO needs |  | MVS | NC
|  |  | Preparing of MOU with parents and program sponsor | Project BEST Coordinators, School Principal, parents, stakeholders/ program sponsor | MVS | 500 | PTA
|  |  | Hiring School Driver to run the school service for the students to ride to and fro with a free fare. | DORP Coordinator, School Head, Administrative Officer | MVS | NC
|  |  | Looking for sponsoring group to maintain and supply the School's Service needs. | DORP Coordinator, Linkage Coordinator, School Head, Administrative Officer |  | NC
|  |  | Budgeting the needs for the School Service (Fuel, other maintenance) | DORP Coordinator, Supply officer, School Head, Administrative Officer | MVS | 70000 | MOOE/ PTA/ Business Partners
|  |  | Implementing the program to save SARDO | Project BEST Coordinators, School Principal, parents, stakeholders/ program sponsor | MVS | 4800 | PTA
|  |  | Monitoring the attendance of SARDO student's performance |  | MVS | 500 | PTA
|  |  | Awarding of save SARDO as completers | School Head, supply officers | MVS | 2000 | MOOE
|  |  | Acomplishing the ACR | Project Chairman and Co- chairman | MVS | NC

## ACCESS hashtag
ANNUAL IMPLEMENTATION PLAN 2018
ACCESS: | Priority Improvement Areas (PIAs)
( STUDENTS' ATTENDANCE)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
HASHTAG ( Help Achieve High performance Teacher Assistance Group) | Reduce number of students habitually cutting classes to 50 out of 120 by 2019 | 25 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC |  | hashtag
|  |  | Organizing project team |  | MVS | NC
|  |  | Crafting of the Modified checklist | Teachers | MVS | 500 | MOOE
|  |  | Checking of the daily attendance in all subjects | Teachers | MVS | 500 | MOOE
|  |  | Consolidating the result | Teacher | MVS | 500 | MOOE
|  |  | Analyzing and sending letters to parents | Department Head | MVS | NC
|  |  | Adopting a student through SAKAY NA- LIBRE PA Program | HASHTAG Coordinator, Advisers, School Head | MVS | NC
|  |  | Compiling the monthly student’s attendance and agreement with parents | Guidance advocate | MVS | NC
|  |  | Acomplishing the ACR |  | MVS | NC

## ACCESS bahay sa paaralan
ANNUAL IMPLEMENTATION PLAN 2018
ACCESS: | Priority Improvement Areas (PIAs)
(STUDENTS' ATTENDANCE)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Bahay Sa Paaralan ko Pansamantalang Tirahan KO | Reduce number of enrollees with incidence of habitual absenteeism from 248 to 50 by 2019 | 66 | Communicating project team and parents | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Conducting Demographic profile per student | All Adviser | MVS | 500 | MOOE
|  |  | Submitting of identified students habitually absent | Teacher Adviser | MVS | NC
|  |  | Conducting meeting with the parents for the construction of Temporay Shelter for Students inside the Campus for those who live in far flung barangays | PTA, School Head, All MVS Personnel | MVS | 1000 | MOOE
|  |  | Signing of MOU construction of Temporay Shelter of Students inside the Campus for those who live in far flung barangays | PTA, School Head, All MVS Personnel | MVS | 1000 | MOOE
|  |  | Budgeting the needs for construction of Temporay Shelter of Students inside the Campus for those who live in far flung barangays | Supply officer, School Head, Administrative Officer | MVS | NC
|  |  | Canvasing and Purchaing the materials needed | Supply officer, School Head, Administrative Officer | MVS | 50000 | PTA/MOOE/ Alumni
|  |  | Submitting Liquadation reports | Supply officer, School Head, Administrative Officer | MVS | NC
|  |  | Acomplishing the ACR | Project Chairman and Co- chairman | MVS | NC

## ACCESS nutritional status
ANNUAL IMPLEMENTATION PLAN 2018
ACCESS: | Priority Improvement Areas (PIAs)
(NUTRITIONAL STATUS)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Pagkain Alagaan, Timbang dagdagan | Decrease the number of severely wasted students from 15 to 0 in 2019 | 5 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Identifying the severely wasted students | All Adviser | MVS | 500 | MOOE
|  |  | Conducting Orientation Related to Proper Health Diet | Teacher Adviser | MVS | 2000 | PTA
|  |  | Feeding Program for the identified severely wasted students during monthly celebration | PTA, School Head, All MVS Personnel | MVS | 12500 | PTA
|  |  | Monitoring and Evaluation of the Project Design | PTA, School Head, All MVS Personnel | MVS | 1500 | MOOE
|  |  | Accomplishing the ACR | Supply officer, School Head | MVS | NC

## QUALITY literacy filipino
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY: | Priority Improvement Areas (PIAs)
(LITERACY)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Kumprehensibong Programa sa Pagbasa | Maipababa ang antas ng kabiguan sa pagbasa sa mga mag-aaral sa baitang 10 mula 52 patungo sa 12 | 10 | Pakikipag-ugnayan sa pangkat at mg magulang | Guro, Punong-guro, stakeholders | MVS | NC |  | Filipino
|  |  | Pagbubuo ng pangkat ng Taga-pangasiwa | Guro, Punong-guro, stakeholders | MVS | NC
|  |  | Pagsasagawa ng pagpupulong sa pagbasa (Pagkukuwento at muling pagkukuwento) | Guro, Mag-aaral sa baitang 10 | MVS | 1000 | MOOE
|  |  | Pagbili ng SMART TV para sa Filipino asignatura | Guro, stakeholders | MVS | 30000 | PTA - Filipino Klab
|  |  | Pagsagawa ng "Film Showing" | Guro, Mag-aaral | MVS | 1000 | MOOE
|  |  | Pagsagawa ng "Summative Test" | Guro, mag-aaral | MVS | NC
|  |  | Pagsagawa ng ACR | Project chairman and co- chairman |  | NC
Pamagat ng Proyekto: Kumprehensibong Programa sa Pagbasa
Pagpahayag ng Suliranin: 52 ng mga mag-aaral sa Baitang 10 ay nasa kabiguang antas
Layunin ng Proyekto: Maipababa ang antas ng kabiguan sa pagbasa sa mga mag-aaral sa baitang 10 mula 52 patungo sa 12
Pangunahing Dahilan: Pagliban sa Klase
Project Work Plan and Budget Matrix
Gawain | Awtput | Petsa ng pagsagawa | Mga taong Responsible | Budget | Pagkukunan ng Budget
Pakikipag-ugnayan sa pangkat at mg magulang | Nakapadala ng liham | Hunyo 2017 | Guro, Punong-guro, stakeholders | NC
Pagbubuo ng pangkat ng Taga-pangasiwa | Nakabuo ng pangkat at taga-pangasiwa | Hunyo 2017 | Guro, Punong-guro, stakeholders | NC
Pagsasagawa ng pagpupulong sa pagbasa (Pagkukuwento at muling pagkukuwento) | Naisagawa ang pagpupulong sa pagbasa (pagkukuwento at muling pagkukuwento) | Dalawang beses sa isang buwan | Guro, Mag-aaral sa baitang 10 | 1000 | MOOE
Pagbili ng SMART TV para sa Filipino asignatura | Nakabili ng SMART TV | Agusto 2016 | Guro, stakeholders | 30000 | PTA - Filipino Klab
Pagsagawa ng "Film Showing" | Naisagawa ang "Film Showing" | Isang beses sa isang linggo | Guro, Mag-aaral | 1000 | MOOE
Pagsagawa ng "Summative Test" | Nasuri ang mga mag-aaral | Quarterly | Guro, mag-aaral | NC
Pagsagawa ng ACR | Naisagawa ng ACR na may MOV's | Quarterly | Project chairman and co- chairman | NC

## QUALITY IRP literacy
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY: | Priority Improvement Areas (PIAs)
(LITERACY)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Improved Reading Program (IRP) | Reduce number of students in frustration Level from 118 to 0 in 2019 | 40 | Communicating project team and parents | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Conducting an institutionalized Reading Assessment/Inventory to students using a standardized test/teacher made test | English/ Reading Teachers | MVS | 2000 | MOOE
|  |  | Identifying and enlistment of non-reader students/project beneficiaries based on the test result | English/Reading Teachers | MVS | NONE
|  |  | Communicating of test results and proposed project to internal and external stakeholders concerned through a conference meeting | SH, Dept. Head /Teachers | MVS | NC
|  |  | Establishing and organizing of reading team composed of teachers | SH, Dept. Head /Teachers | MVS | NC
|  |  | Evaluating of Reading Teachers’ Pedagogical Skills, Content, Knowledge on the Teaching of Reading using a survey questionnaire | Reading Team/Teachers | MVS | 100 | MOOE
|  |  | Conducting of an INSET on Teaching Reading | SH. Reading Team/Teachers | MVS | 10000 | MOOE
|  |  | Crafting of Development Reading Intervention Program: Gathering of instructional inputs/reading materials , Production/ Construction of instructional inputs /reading materials | SH, and Reading Team/Teachers | MVS | 30000 | MOOE
|  |  | Provisioning varied and appropriate reading materials in the said Reading Room/Center | Reading Teachers | MVS | 4000 | MOOE
|  |  | Preparing schedule for the intervention program implementation |  | MVS
|  |  | Establishing and organizing Reading Club composed of students in the pilot classes or student achievers | Reading team/ Teacher and students | MVS | NC
|  |  | Conducting workshop on doing individualized Reading Tutorial for student reading buddies | Reading Team/ Teachers and Reading Club | MVS | 5000 | MOOE
|  |  | Implementing actual Intervention program | Student beneficiaries/Teachers | MVS | 5000 | MOOE
|  |  | Accomplishing the ACR | Project Chairman and Co- chairman | MVS | NC

## quality NUMERACY
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY: | Priority Improvement Areas (PIAs)
(Numeracy)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
I LOVE MATH Program | Decrease the number of students classified as poor in terms of performance in Mathematics from 217 to 50 in 2019 | 56 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head | MVS | NC
|  |  | Identifying students with difficulties in certain Mathematical Concept | Mathematics Teachers | MVS | NC
|  |  | Peer tutoring during ICL | Mathematics Teachers | MVS | 1000 | MOOE
|  |  | Giving of specialized activities to identified students with difficulties in certain Mathematical concept | MATH CLUB OFFICERS and Members | MVS | 1000 | MOOE
|  |  | Empowering advanced students to mentor peers. | Students | MVS | 1000 | MOOE
|  |  | Monitoring and evaluating students' performances in Mathematics | Mathematics Teachers | MVS | NC
|  |  | Accomplishing the ACR | Project Chairman and Co- chairman | MVS | NC

## QUALITY project best perfo indi
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY: | Priority Improvement Areas (PIAs)
(PERFORMANCE INDICATOR)
Project Title | Procject Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Project BEST (Barangay Education Strategic Team) | By 2019, promotion rate will increase from 95.35% -100% | 3% increase | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Conducting a Quarterly meeting with the Project BEST members. | Principal, Project BEST Coordinator, Barangay Council | MVS | 5000 | MOOE
|  |  | Monitoring students who are at risk of Dropping out (SARDO) | Class Adviser, Project BEST Coordinator, Barangay Council | MVS | 4000 | MOOE
|  |  | Awarding of stakeholders who have an exemplary contribution to the success of the program | Principal, School-Based Awards and Recognition Committee,Project BEST Coordinator | MVS | 1000 | MOOE
|  |  | Accomplishing ACR | Project Chairman and Co- Chairman | MVS | NC

## programs non aca sports
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY: | Priority Improvement Areas (PIAs)
(COMPETITION ON NON- ACADEMIC)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
MVSports "ABAG" Program | By 2019, promotion rate will increase from 95.35% -100% | 3% increase | Communicating project team and parent | Sports Coordinator,Chairman, Co-Chairman Coaches, Trainers, and Athletes | MVS | NC |  | sports
|  |  | Organizing sports club and encouraging students ( specially SARDO) to be part of any sports they felt could develop them holistically |  | MVS | NC
|  |  | Attending training and seminars to be constantly updated of the, rules and regulations, and new sports trends | Sports Coordinator, Coaches, Trainers, and Athletes | No exact Venue | 20000 | MOOE, Sports Fund
|  |  | Adhering to the special training program/design prepared | School Head, Sports Coordinator, Coaches, Trainers, and Athletes | MVS | NC
|  |  | Providing every active sports discipline with the necessary gears and equipment to be used for practice and game proper | School Head, Supply Officer, Sports Coordinator, Coaches and Athletes |  | 200000 | MOOE, LGU, GPTA, Sports Fund
|  |  | Organizing quarterly sports festival and compete in athletic meets | School Head, Sports Coordinator, Coaches, Trainers, and Athletes | MVS | 15000 | MOOE, LGU, GPTA, Sports Fund
|  |  | Close monitoring of each member's responsibilty and accountability particularly in balancing their sports with their academics | School Head, Sports Coordinator, Teachers,Teacher-Adviser, Coaches, Trainers, and Athletes |  | NC
|  |  | Awarding of Sports club members, benefactors and stakeholders who have done exemplary performance and heartwarming contributions to success of the program | School Head, Sports Coordinator, Teachers,Teacher-Adviser, Coaches, Trainers, Athletes and stakeholders | MVS | 1000 | MOOE, Sports Fund
|  |  | Giving incentives in cash to those athletes who are advancing for PALARONG PAMBANSA |  | MVS | 80000 | MOOE/PTA/ LGU
|  |  | Accomplishing the ACR | Sports Chairman |  | NC

## SPORTS ARNIS)
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY: | Priority Improvement Areas (PIAs)
(Sports)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
MVS ARKADO (Arnis-Kali-Do) | By 2019, at least 30% of the MVS ARKADO team will participate in the EVRAA Meet | 10% | Communicating, organizing and staffing MVS ARKADO Club | ARKADO Club Advisers/ Officers/ Members | MVS | Php 500.00 | MOOE/ PTA
|  |  | Planning and Budgeting Training Programs (Arnis Sports facility and equipment) | School Heads/ Arnis Coach&Trainer/ Stakeholders | MVS | Php 143, 000.00 | MOOE/ PTA/ LGU
|  |  | Conducting Arnis Sports Clinic | School Heads/ Arnis Coach&Trainer/ Student Athletes/ Stakeholders | MVS | Php 2, 000.00 | MOOE/ PTA/ LGU
|  |  | Participating Arnis Competitions in Athletic Meets | School Heads/ Arnis Coach&Trainer/ Student Athletes/ Stakeholders | No exact venue | Php 25, 000.00 | MOOE/ LGU/ PTA
|  |  | Awarding and Promoting MVS ARKDO Club members |  | MVS | Php 1, 500.00 | MOOE/ PTA
|  |  | Assessing the conducted activities |  | MVS | Php 500.00 | MOOE/ PTA

## schoo, pasidungog
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY |  | Priority Improvement Areas (PIAs)
School-based Awards and Recognition System
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
School-based Awards and Recognition System | By 2019, at least 11% of the MVS teachers will be recognized in the Division PASIDUNGOG | 2% | Communicating and organizing SAR project team | School Heads, faculty and stakeholders | MVS | NC
|  |  | Reviewing of the School-based Pasidungog Nomination Guidelines | SAR project team/ Assessment committee | MVS | 2000 | MOOE
|  |  | Orienting MVS faculty and stakeholders on the nomination guidelines | SAR project team/ Assessment committee/ Faculty/ Stakeholders | MVS | 500 | MOOE
|  |  | Selecting of MVS faculty nominees | SAR project team/ Assessment committee | MVS | 2000 | MOOE
|  |  | Selecting of MVS stakeholders nominees | SAR project team/ Assessment committee | MVS | 2000 | MOOE
|  |  | Validating of the School-based Pasidungog nominees | SAR project team/ Assessment committee | MVS | 500 | MOOE
|  |  | Awarding of the outstanding School-based Pasidungog candidates | School Heads, SAR project team, faculty and stakeholders | MVS | 5000 | MOOE
|  |  | Assessing the conducted activities | SAR project team | MVS | 500 | MOOE

## programs academ math dlp
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY: | Priority Improvement Areas (PIAs)
(COMPETITION ON ACADEMIC)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
MATHEMATICS ADVANCE TUTORING ON HIGHLY-DEVELOPED LEARNERS Program (MATH-DLP) | By 2019, 66% of the students who participated in the Division Math contest can achieve the Top 3 spots | 22% | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | 1, 000 | MOOE | dlp math
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | 1, 000 | MOOE
|  |  | Identifying potential learners to be part of the MATH-DLP | Mathematics Teachers | MVS | 5000 | MOOE
|  |  | Conducting specialized training and review on potential learners. | Students | MVS | 5000
|  |  | Participating MATH Quiz and MTAP DepED Math Challenge | School Head, Supply Officer | MVS | 15000
|  |  | Accomplishing the ACR | Project Chairman and Co- Chairman | MVS | 1, 000 | MOOE

## programs aca journa
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY: | Priority Improvement Areas (PIAs)
(COMPETITION ON ACADEMIC)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
The Meridian - Journalism | Develop 45 young journalists to compete in the higher academic competition by 2019 | 15 | Communicating project team and parent | Teachers, School Head, Stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head, Stakeholders | MVS | NC
|  |  | Identifying potential students to be part of the JOURNALISM | English Teachers and School Pub. Adviser | MVS | NC
|  |  | Planning and Budgetting training programs for CAMPUS JOURNALISM | School Pub. Adviser and Editorial Staff | MVS | 2000 | School Pub. Funds
|  |  | Procuring of facilities for radio broadcasting and TV Newscasting | School Pub. Adviser, Editorial Staff and PTA |  | 250000 | LGU, Alumni, School Pub. Funds
|  |  | Conducting specialized training on writing, radio broadcasting and TV newscasting to identified potential competitors. | School Pub. Adviser and Editorial Staff |  | 7000 | School Pub. Funds
|  |  | Participating in School's Press Conferences | School Pub. Adviser and identified competitors | No exact Venue | 60000 | School Pub. Funds
|  |  | Production of Tabloid - The Meridian | School Pub. Adviser and Editorial Staff | Ormoc Printing Press | 25000 | School Pub. Funds
|  |  | Monitoring and Evaluation of the Project Design | SMEA and School Pub. Adviser |  | 1500 | MOOE
|  |  | Accomplishing the ACR | School Pub. Adviser and Editorial Staff |  | NC

## programs quali technolympics
ANNUAL IMPLEMENTATION PLAN 2018
QUALITY: | Priority Improvement Areas (PIAs)
(COMPETITION ON NON- ACADEMIC)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
TECHNOLYMPICS | Increase number of participation in different skills from 2 to 8 in 2019 | 3 | Communicating project team and parent | Teachers, School Head, Stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head, Stakeholders | MVS | NC
|  |  | Identifying potential students to be part of the Technolympics Competition | STVE Teachers | MVS | NC
|  |  | Planning and Budgetting training programs for Technolympics parcticipants | STVE Teachers, Coach | MVS | 2000 | STVE Funds
|  |  | Procuring of supplies and facilities for the proper training | STVE Teachers, Coach, supply officer | MVS | 50000 | STVE Funds/ MOOE
|  |  | Conducting specialized training on different skills to be participated in the Technolympics Competition | STVE Teachers, Coach | MVS | 500 | STVE Funds/ MOOE
|  |  | Participating in the Technolympics Competition | STVE Teachers, Coach | No exact Venue | 15000 | STVE Funds/ MOOE
|  |  | Accomplishing the ACR | STVE Coordinator | MVS | NC

## GOVERNANCE CFSS
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
CFSS
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Class – Away- School | Conduct 3 to 7 CFSS sessions in different barangay with Project BEST in 2019 | 1 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Orienting teachers and students on the 7 goals of CFSS | Advisers, Guidance Advocate | MVS | 1000 | MOOE
|  |  | Accomplishing the checklist of activities to be conducted per item per goal in order to track the progress of becoming a CFS. | SSG Adviser | MVS | 500 | MOOE
|  |  | Accomplishing the ACR | CFSS Chairman | MVS | NC

## repair and maintenance
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
CONSTRUCTION, REPAIR AND MAINTENANCE PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Repaired today, Damaged away | Increase accomplishment in school's repair and maintenance from 40% to 100% in 2019 | 20% | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Providing column truss, tool room and roofing of temporary Automotive Shop | Carpenter | MVS | 100000 | MOOE/PTA
|  |  | for SHS Repaint walls and roofs of administration building | Physical Facilities Officer and skilled personnel | MVS | 30000 | MOOE
|  |  | Preparing of program of work. | School head, | MVS | 100000 | LGU/PTA and MOOE
|  |  | Seeking assistance for BUB fund | Physical development | MVS | 2000 | MOOE
|  |  | Presenting the need to LGU for equity. | Officers, Budget officers | MVS | 25000 | MOOE
|  |  | Repairing ceiling and roofing HE building | Physical Facilities Officer and skilled personnel | MVS | 10000 | MOOE/PTA
|  |  | Constructing covered walk | SHS Teacher in welding, students and skilled personnel | MVS | 50000 | MOOE
|  |  | Constructing rooms/ offices | Supply officer and skilled personnel | MVS |  | MOOE/ other donations
|  |  | a. Guard house |  |  | 20000
|  |  | b. Office of DRR and MAPEH |  |  | 10,00
|  |  | c. Clinic/ Guidance room |  |  | 20000
|  |  | d. Science Laboratory |  |  | 50000
|  |  | e. Classroom for TVL |  |  | 50000
|  |  | Constructing I LOVE MVS Mark |  |  | 15000 | Alumni Donation
|  |  | Repiping for water system | Supply officer and skilled personnel |  | 100, 000 | MOOE
|  |  | Replacing damaged fluorescent bulb/lamp, transformer, circuit breaker, old electrical wirings | Supply officer and skilled personnel |  | 150000 | MOOE
|  |  | Repainting Basketball Court lines | Supply officer and skilled personnel |  | 2000 | MOOE
|  |  | Maintaining laptop printers, projector and flash drive in good condition | Electrician, Physical Facilities Coordinator |  | 5000 | MOOE
|  |  | Maintaining computer tables, door and window grills for computer safe keeping | SH, Physical Facilities Coordinator |  | 50000 | MOOE/ Donations
|  |  | Maintaining Electrical facilities- wirings, outlets, switch, circuit breaker etc. | Electrician, Physical Facilities Coordinator |  | 5000
|  |  | Installing air conditioning to provide ventilation for both students and computers | Electrician, Physical Facilities Coordinator |  | 10000
|  |  | Repairing Modular Homes for the faculty and staff | Physical Facilities Coordinator |  | 20000 | MOOE
|  |  | Repairing and and Maintaining the School Vehicle in good condition | Supply officer, School Head, School Vehicle in-charge |  | 150000 | MOOE
|  |  | Accomplishing the ACR | Repair and Maintenance Chairman |  | NC

## GOVERNANCE LINKAGE
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
PARTNERSHIP AND LINKAGES
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Partnership and Linkages | Intensify linkage among stakeholders from 5 to 10 in 2019 | 2 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing data according to priority of importance. Adjust data of the SRC by quarter. Prepare AIP . | School Head | MVS | NC
|  |  | Inviting parents and stakeholders thru a letter | Teachers and SH | MVS | NC
|  |  | Identifying organization to adopt a student for school support | Section Adviser and Guidance Counselor | MVS | 5000 | Stakeholders
|  |  | Converging of stakeholders | SHS coordinator and Guidance Counselor | MVS | 500 | MOOE
|  |  | a. Students' Development | School Head | MVS | NC
|  |  | b. Physical Facilities |  | MVS | NC
|  |  | c. Teachers Development |  | MVS | NC
|  |  | d. Status of Programs and Projects |  |  | NC
|  |  | Categorizing the achievements of the school thru the AIP/SIP and those that have been the concern during the meeting | School Head |  | 2000 | PTA Fund
|  |  | Delivering of SOSA | School Head |  | NC
|  |  | Presenting future plans of the School in the next 3 years. | School Head |  | 500 | MOOE
|  |  | Accomplishing the ACR | Support and Linkage Chairman |  | NC

## GOVERNANCE sbm
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
SCHOOL- BASED MANAGEMENT
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
School Based Management Level 3 Accreditation Program | Meet the SBM level 3 accreditation criteria from 70% to 100% in 2019 | 10% | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | 2000 | MOOE
|  |  | Organizing project team |  | MVS | 2000 | MOOE
|  |  | Organizing four (4) committees and assign each team with one principle. | Head Designate, Teachers, SBM Coordinator | MVS | 2000 | MOOE
|  |  | Updating and arranging artifacts and MOVs according to principle and levels. | SBM Coordinator and School Head | MVS | 15, 000 | MOOE
|  |  | Conducting the D-O-D process and assess, analyze to get SBM Level of Practice | SBM Coordinator and School Head | MVS | 5, 000 | MOOE
|  |  | Accomplishing the ACR | SBM Chairman and Co- chairman | MVS | 10, 000 | MOOE
Project Title: School Based Management Level 3 Accreditation Program
Problem Statement: There 's a decrease of enrollment by 2.65% that greatly affects ACCESS which is 45% of the SBM accreditation criteria.
Project Objective Statement: Meet the SBM level 3 accreditation criteria from 70% to 100% in 2019
Root Cause: did not meet the cirteria
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | 2000 | MOOE
Organizing project team | Organized project team | June |  | 2000 | MOOE
Organizing four (4) committees and assign each team with one principle. | Achieved SBM-PASBE Level 3 Accreditation. | June 15- 30 | Head Designate, Teachers, SBM Coordinator | 2000 | MOOE
Updating and arranging artifacts and MOVs according to principle and levels. | Updated artifacts and MOV's | 2017-08-01 | SBM Coordinator and School Head | 15, 000 | MOOE
Conducting the D-O-D process and assess, analyze to get SBM Level of Practice | Conducted D-O-D | 2017-08-15 | SBM Coordinator and School Head | 5, 000 | MOOE
Note: Please record also the date of monitoring per project Please attach this form to the AIP template
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2017-2019 | SBM Chairman and Co- chairman | 10, 000 | MOOE

## GOVERNANCE TEACHER DEV. PROG)
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
TEACHERS' PROFESSIONAL DEVELOPMENT PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
TEACHERS' PROFESSIONAL DEVELOPMENT PROGRAM | Encourage 40 teachers to enroll in any graduate studies in 2019 | 15 | Communicating project program's rationale and targets | Project Chairman, Teachers, School Head, stakeholders | MVS | NC
|  |  | Re-visiting IPPD & update teachers' competency level | Teachers Dept. Head, & SH | MVS | NC
|  |  | Preparing individual professional development plan | Teachers Dept. Head, & SH | MVS | NC
|  |  | Identifying teachers' Strengths and Needs | Project chairman | MVS | NC
|  |  | Conducting INSET | Teachers Dept. Head, & SH | MVS | 11500 | MOOE
|  |  | Identifying teachers to attend the Division, Regional and National teaching- related trainings | Teachers | No exact Venue | 41250 | MOOE
|  |  | Accomplishing the ACR | Project Chairman and Co- chairman | MVS
|  |  | Liquidating travel | Department Heads/ Teachers | MVS | 6000 | PTA Fund
|  |  | Acomplishing the ACR | Project Chairman and Co- chairman | MVS | NC

## GOVERNANCE YES-O
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
YES- O PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
MVS YES-O CAMPERS - Batang Maka-agham, Pag-asa ng Kalikasan | Involve 70 of the 110 YES-O registrants in community and eco- friendly activities in 2019 | 25 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC |  | yes o
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Regularly review class schedule to enrich and proficient students to participate in Science Quiz Bee | Science Teachers, YES-O Campers | MVS | 10000 | Science Club Fund
|  |  | Organizing environmental program and encouraging community to be involved | MVS Community, LGU, NGO’s | MVS
|  |  | Acomplishing the ACR | Project Chairman and Co- chairman | MVS | NC

## GOVERNANCE GULAYAN
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
GULAYAN SA PAARALAN PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Tanim ko - Ani ko | By 2019, Gulayan sa Paaralan Program income generation will increase to 50%. | 17% | Communicating and organizing project team and stakeholders. | GPP Project Team, Stakeholders | MVS | 500 | MOOE
|  |  | Planning and budgeting training programs for Gulayan sa Paaralan Program. |  | MVS | 5000 | MOOE
|  |  | Orienting the stakeholders about Gulayan sa Paaralan Program. | GPP Project Team | MVS | 200 | MOOE
|  |  | Implementing the Gulayan sa Paaralan Program. . Securing seeds locally adapted vegetable varieties. .Preparing the garden soil. .Planting of vegetable variety. | GPP Project Team | MVS | 2000 500 | MOOE
|  |  | Weeding and cultivating. | GPP Project Team | MVS | 500
|  |  | Harvesting and marketing of the vegetables. | GPP Project Team | MVS | 500 | MOOE
|  |  | Assessing the conducted activities. | GPP Project Team |  | 500 | MOOE

## governcnenon aca scouting
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNACE | Priority Improvement Areas (PIAs)
SCOUTING PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
MVS Scouting Movement | Increase number of members to 244 out of 488 BSP potential and 296 out of 592 GSP potential in 2019 | 180 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing scouting to improve the total personality of young students | MAPEH Teachers, Scouting coordinators | MVS | 10000 | PTA- Scouting Funds
|  |  | Sending scouts/ coordinators for trainings | MAPEH Teachers, Scouting coordinators | No exact venue | NC
|  |  | Advancement of scouters/ providing awards/ merits for outstanding scouters | MAPEH Teachers, Scouting coordinators | MVS | 5000 | MOOE
|  |  | Accomplishing the ACR | Project Chairman and co- chairman |  | NC

## GOVERNANCE DRRM
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
DRRM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
MVS ERUF (Emergency Response Unit Force) | By 2019, 80% of the MVS community are capacitated for for disaster risk reduction management before, during and after the occurrence of hazards. | 27% | Communicating and organizing project team. | SDRRM Coordinator/ MVS Employees and Stakeholders | MVS | 500 | MOOE
|  |  | Planning and Budgeting Training Programs for DRR Preparedness | SDRRM Project Team | MVS | 5000 | MOOE
|  |  | Preparing Emergency Response Plan | SDRRM Project Team | MVS | 1500 | MOOE/ PTA
|  |  | Crafting of the School Contingency Plan | School Heads/ SDRRM Project Team | MVS | 1500 | MOOE
|  |  | Procuring rescue equipment and other emergency paraphernalia | School Heads/ SDRRM Project Team | No exact Venue | 100000 | MOOE/ LGU/ PTA
|  |  | Procuring Hand held Radio | School Heads/ SDRRM Project Team | No exact Venue | 50000 | MOOE/ NGO
|  |  | Institutionalizing school additional Early Warning System | School Heads/ SDRRM Project Team/ MVS Stakeholders | MVS | 18000 | MOOE/ NGO
|  |  | Formulating of Evacuation Procedures | School Heads/ SDRRM Project Team | MVS | 500 | MOOE
|  |  | Conducting School-based DRRM Training/ Workshop | School Heads/ SDRRM Project Team/ MVS Stakeholders | MVS | 2500 | MOOE/ PTA/ LGU
|  |  | Conducting School Quarterly Emergency/ Disaster Drills | BFP, PNP, RHU, LDRRM, SDRRM Project Team, Employees, and Students | No exact Venue | 2000 | MOOE
|  |  | Integrate DRR Education into the carrier subjects/ student organizations | School Heads/ SDRRM Project Team/ Teachers
|  |  | Assessing the conducted activities | School Heads/ SDRRM Project Team/ Teachers and Stakeholders |  | 500 | MOOE/ PTA
Project Title:MVS ERUF (Emergency Response Unit Force)
Problem Statement: Only 22% of the MVS community are capacitated for DRRM
Project Objective Statement: By 2019, 80% of the MVS community are capacitated for for disaster risk reduction management before, during and after the occurrence of hazards.
Root Cause: Disaster risk reduction management preparedness is highly recommended
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating and organizing project team. | Communication Letters/ Organized SDRRM project team | 2017-06-01 | SDRRM Coordinator/ MVS Employees and Stakeholders | 500 | MOOE
Planning and Budgeting Training Programs for DRR Preparedness | Workshop/ Training Program Matrix | 2017-06-01 | SDRRM Project Team | 5000 | MOOE
Preparing Emergency Response Plan | Emenrgency Response Plan/ School Development Plan Framework | 2017-07-01 | SDRRM Project Team | 1500 | MOOE/ PTA
Crafting of the School Contingency Plan | MVS DRRM Contingency Plan | 2017-07-01 | School Heads/ SDRRM Project Team | 1500 | MOOE
Procuring rescue equipment and other emergency paraphernalia | Budget Plan/ Transparency Reports | 2017-08-01 | School Heads/ SDRRM Project Team | 100000 | MOOE/ LGU/ PTA
Institutionalizing school Early Warning System | School Warning System/ Communication Plan | 2017-09-01 | School Heads/ SDRRM Project Team/ MVS Stakeholders | 80000 | MOOE/ PTA
Formulating of Evacuation Procedures | SOP Plans/ Hazards/ Evacuation Maps | 2017-09-01 | School Heads/ SDRRM Project Team | 500 | MOOE
Conducting School-based DRRM Training/ Workshop | Communication Letters/ Certificates/ ACR/ Narrative Reports | 2017-09-01 | School Heads/ SDRRM Project Team/ MVS Stakeholders | 2500 | MOOE/ PTA/ LGU
Conducting School Quarterly Emergency/ Disaster Drills | Communication Letters/ ACR/ Narrative Reports | Quarterly | BFP, PNP, RHU, LDRRM, SDRRM Project Team, Employees, and Students | 2000 | MOOE
Integrate DRR Education into the carrier subjects/ student organizations | Integrated DRR education in the lesson plan/ Sports/Scouting training designs | Quarterly | School Heads/ SDRRM Project Team/ Teachers
Assessing the conducted activities | Communication Letters/ ACR/ Narrative Reports/ Evaluation Results | Quarterly | School Heads/ SDRRM Project Team/ Teachers and Stakeholders | 500 | MOOE/ PTA

## GOVERNANCE cpp
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
CHIL PROTECTION POLICY
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Action - Reaction, Child-Protection | Eliminate incidence of bullying from 40% to 0 and promote Children's Rights in 2019 | 14% | Communicating project team and parents | Teachers, School Head, stakeholders | MVS | NC | MOOE
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Convening the class officers for an orientation meeting | SSG Adviser and Student Leaders | MVS | 5000 | MOOE
|  |  | Formulating a plan of activities on CPP to implement advocacy | SSG Adviser and Student Leaders | MVS | 10000 | MOOE, LGU
|  |  | Coordinating with the other organizations and offices if problem exist that violates the rights of children | SSG Adviser and Student Leaders | MVS | 1000 | MOOE
|  |  | Accomplishing the ACR | CPP Chairman | MVS | NC

## GOVERNANCE i connecte
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
INTERNET CONNECTION
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
I- connected | Provide internet connection from 0 to 2 in 2019 | 1 | Communicating project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Conducting meeting to budget officer and School heads | ICT coordinator, Budget officer and School heads | MVS | NC
|  |  | Canvassing materials needed for Internet intallation | ICT coordinator, Budget officer and School heads | MVS | NC
|  |  | Applying contract for Internet connection for the Senior high School laboratory and for the Office of the Department Heads | School Head, Supply officer | MVS | NC
|  |  | Allocating Budget for Monthly payment for internet connection | School Head, Supply officer | MVS | 10000 | MOOE/ Donations
a. Office of the Department Heads
b. Senior high School laboratory
|  |  | Liquadating Expenses | School Head, Supply officer |  | 500 | MOOE

## GOVERNANCE ICT LAC SESSION
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
ICT LAC session
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
ICT LAC session | Increase number of teachers from 26 to 53 that were able to perform basic skills in word, excel powerpoint application | 5 | Communicating project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Signing of Agreement between the teacher and ICT Coordinator regarding the schedule of session | Teachers and ICT Coordinator | MVS
|  |  | Prepare Training Design for ICT LAC Session | ICT Coordinator | MVS | 500
|  |  | Discussing and applying session will initiated regarding MS Application such as Word, Excel power point, etc. | Teachers and ICT Coordinator | MVS
|  |  | A session for registering and opening e-mail accounts and visiting other DepEd portals such as LRMDS, DepEd Websites, Searching in Google engine, etc. | Teachers and ICT Coordinator | MVS | 2000 | DepEd DCP
|  |  | Conducting Computer usage and net usage assessment | Teachers and ICT Coordinator |  | 1000 | DepEd
|  |  | Using of desktop computers to formulate communications | School Head, Designate Head, Teachers, and Finance personnel |  | 2000 | MOOE
|  |  | Acomplishing the ACR | ICT Coordinator, ICT Teacher |  | NC

## GOVERNANCE SBM WINS
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
WASH WINS
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
SBM WiNs | Increase accessibility of potable water from 1 to 3 in 2019 | 1 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Repairing or replacing damaged faucet and fix leaked pipes | Plumber and Physical Coordinator | MVS | 20000 | PTA Fund
|  |  | Installing water tanks or purchase water purifier |  | MVS | 15000 | MOOE/NGO/ Alumni
|  |  | Constructing new Comfort Rooms | Skilled personnel | MVS | 15000 | MOOE/PTA Fund
|  |  | Constructing additional hand washing faciltiy | Skilled personnel | MVS | 10000 | MOOE/NGO/ Alumni
|  |  | Constructing Deep well | Skilled personnel | MVS | 10000 | MOOE/PTA Fund
|  |  | Procuring water pump | Supply officer | no nexact venue | 30000 | MOOE/other donations
|  |  | Conducting lecture on Proper Sanitation and Hygiene to orient students | Teacher and students | MVS | 2000 | HRPTA/Fund
|  |  | Providing trash bins with proper label | Eco-Friendly coordinator and advisers |  | 6000 | Classroom Project/HRPTA Fund
|  |  | Conducting deworming twice a year | Advisers, RHU, DepEd Nurses and students |  | 8000 | 4Ps Sponsorship
|  |  | Examine student's dental conditions | RHU, DepEd Dentist |  | 20000 | MOOE
|  |  | Accomplishing the ACR | Project Chairman and Co- Chairman |  | NC

## GOVERNANCE eco friendly
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
ECO-FRIENDLY
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Sustainable Eco-friendly School Program | Implement the Program on Sustainability of the Eco-friendly Environment from 50% to 100% in 2019 | 17% | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Providing compost heap/ pit and campaigning for a proper segregation and disposal of wastes in school. | Teachers | MVS | 3000 | Science Club Fund
|  |  | Providing drainage and keeping the environment clean | SSG Officers | MVS | 20000 | SSG, MOOE
|  |  | Segregating garbage and putting it in compost heap/pit to decomposed into an organic material. | SSG Officers | MVS | NC
|  |  | Implementing the junk- food free in the school canteen. | Canteen Manager, Vendors | MVS | NC
|  |  | Implementing the '' BOTE MO - I SHOOT MO- MAGING PERA TO'' program | Teachers, Students | MVS | NC
|  |  | Implementing the 5 O’ clock habit (in the afternoon) “ The Picking up of Trashes around the school campus) | Teachers, Students | MVS | NC
|  |  | Collecting recyclable and salable bottles |  |  | 1000 | SSG
|  |  | Eco friendly members with SSG Officers from eco- friendly motivated students and teachers | Teachers, Students | MVS | NC
|  |  | Organizing the materials stored in “Material Recovery Facility” | Science Teachers, PTA | MVS | NC
|  |  | Assigning the Science Club to spearhead the tree planting activity. | Science Club Advisers, Students | MVS | 5000 | LGU
|  |  | Coordinating with the community for an eco-friendly activities and projects | Teacher and students | MVS | NC
|  |  | Accomplishing the ACR | Eco- friendly Chairman and co- chairman | MVS | NC
Project Title: Sustainable Eco-friendly School Program
Problem Statement: Sustained Eco-friendly School Program
Project Objective Statement: Implement the Program on Sustainability of the Eco-friendly Environment from 50% to 100% in 2019
Root Cause: Technical assistance not provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Providing compost heap/ pit and campaigning for a proper segregation and disposal of wastes in school. | Implemented and incorporated programs on Eco- friendly in Science and TLE lessons | June 2017- April 2018 | Teachers | 3000 | Science Club Fund
Providing drainage and keeping the environment clean |  | June 2017- April 2018 | SSG Officers | 20000 | SSG, MOOE
Segregating garbage and putting it in compost heap/pit to decomposed into an organic material. | Implemented and incorporated programs on Eco- friendly in Science and TLE lessons | June 2017- April 2018 | SSG Officers | NC
Implementing the junk- food free in the school canteen. | Items in the school canteen are junk food free | June 2017- April 2018 | Canteen Manager, Vendors | NC
Implementing the '' BOTE MO - I SHOOT MO- MAGING PERA TO'' program | Generated income of the program | June 2017- April 2018 | Teachers, Students | NC
Implementing the 5 O’ clock habit (in the afternoon) “ The Picking up of Trashes around the school campus) | Maintained clean and green campus. | June 2017- April 2018 | Teachers, Students | NC
Collecting recyclable and salable bottles |  | June to April 2018 |  | 1000 | SSG
Eco friendly members with SSG Officers from eco- friendly motivated students and teachers |  | June 2017- April 2018 | Teachers, Students | NC
Organizing the materials stored in “Material Recovery Facility” | Organized MRF | 2017-06-01 | Science Teachers, PTA | NC
Assigning the Science Club to spearhead the tree planting activity. | Planted 200 hard wood trees in the school campus | June 2017- Sept. 2017 | Science Club Advisers, Students | 5000 | LGU
Coordinating with the community for an eco-friendly activities and projects | Coordinated eco-friendly activities with other community clubs | June to April 2017 | Teacher and students | NC
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2017-2017 | Eco- friendly Chairman and co- chairman | NC

## GOVERNANCEbrigada eskwela
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
BRIGADA ESKWELA PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
BRIGADA ESKWELA IN BAYANIHAN SYSTEM | Increase participation of students and parents in Brigada Eskwela from 500 to 750 in 2019 | 83 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Establishing strong partnership thru meetings, assemblies and other school activities | Stakeholders, SH & Teachers | MVS | NC
|  |  | Preparing program of work | Stakeholders, SH, Teachers & brigada coordinator | MVS | NC
|  |  | Encouraging stakeholders to join the weeklong school maintenance prior to opening of classes | SH, Teachers, Students Stake-holders | MVS
|  |  | Doing work thru bayanihan system such as minor repair, cleaning the school classrooms, gardens and the entire campus, pruning trees, fixing chairs and seats etc. | Parents, alumni, BHWs, BFP, Military men, LGU, Brgy Officials | MVS | 250000 | BE donors
|  |  | Accepting cash or in kind donations and sign Certificate of Acceptance | Alumni, SH, other civic spirited citizens | MVS | 100000 | PTA
|  |  | Documenting the work before, during and after the BRIGADA ESKWELA | BRIGADA ESKWELA Documenter | MVS | 1000 | MOOE
|  |  | Accomplishing the ACR | BRIGADA ESKWELA Chairman | MVS | NC

## GOVERNANCE gad
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
GAD
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Reinforced Gender Equality in School | Conduct orientation on Women’s Right from 0 to 6 in 2019 | 2 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Attending Seminar/ Team building | Teachers, Principal, Guidance Counselor, Non-teaching Staff | MVS | 5000 | PTA/ MOOE
|  |  | Institutionalizing celebration activities | PTA, Teachers, Principal, Guidance counselor | MVS | 500
|  |  | Discussing GAD lessons in all subjects | Teachers | MVS | NC
|  |  | Celebrating Women’s month | Stake holder, teacher, PTA, Administration | MVS | 1000 | PTA/MOOE
|  |  | Conducting Career guidance on choosing best career path | Teacher, PTA, Guidance counsellor | MVS | 500 | PTA
|  |  | Accomplishing activity completion report | Guidance Counselor | MVS | 500 | MOOE

## GOVERNANCE SMEA
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
SMEA
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
School Monitoring, Evaluation and Adjustment | On time submission of reports by 50 out 53 teachers in 2019 | 2 | Communicating project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Organizing and orienting SMEA Team functions and responsibilities | SMEA Team | MVS | 500 | MOOE
|  |  | Monitoring and gathering data of school programs and projects | SMEA Team | MVS | 500 | MOOE
|  |  | Validating and adjusting results of school accomplishments | SMEA Team | MVS | 500 | MOOE
|  |  | Organizing MOVs to support the data and its accomplishments | SMEA Team | MVS | 500 | MOOE
|  |  | Analyzing the result and finding out the causes | SMEA Team and Teachers | MVS | NC
|  |  | Identifying the Issues and problems for RESOLUTION and identify the intervention to address the need | EMIS Coordinator, IT Teacher, DepT Heads | MVS | NC
|  |  | Accomplishing the ACR | SMEA Chairman | MVS | NC

## GOVERNANCE SENIOR HOGH
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
SENIOR HIGH SCHOOL PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Implementation of Senior High School under TVL | Provide facilities and equipment for K-12 from 25% to 100% in 2019 | 25% | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Procuring SMART TV and LED projector | SHS coordinator, supply officer | no exact venue | 65000 | SHS MOOE
|  |  | Purchasing furnishings | SHS coordinator, supply officer | MVS | 109000 | SHS Budget
|  |  | Purchasing SHS supplies | SHS coordinator, supply officer | MVS | 100000 | SHS Budget
|  |  | Purchasing reference books | SHS coordinator, supply officer | MVS | 10000 | SHS Budget
|  |  | Budgeting for Year end expenses |  | MVS | 10000 | SHS Budget
|  |  | Purchasing materials for Certificates and awards |  | MVS | 20000 | SHS Budget
|  |  | Budgeting for Water supplies |  | MVS | 30000 | SHS Budget
|  |  | Purchasing of Auto, SMAW and Beauty care supplies |  | MVS | 57000 | SHS Budget
|  |  | Constructing library for Senior High School | SHS coordinator, supply officer | MVS | 20000 | SHS Budget/other donations
|  |  | Sending letters to barangay chairman to disseminate information for SHS enrolment | Linkage Chairman |  | 500 | MOOE
|  |  | Conducting advocacy and early registration for grade 11 | Grade 10 teachers |  | 500 | MOOE
|  |  | Displaying of streamers | SHS Coordinator |  | 1000 | MOOE
|  |  | Acomplishing the ACR | Project Chairman and co- chairman |  | NC

## GOVERNANCE LYRE)
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
Drum and Lyre Corps
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Drum and Lyre Corps | Increase the number of functional drums and lyres equipment from 5 to 10 in 2019 | 2 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Registering prospect DLC members | Chairman and officers of DLC | MVS | 50 pesos/ student | Membership Funds
|  |  | Purchasing of instruments | DLC Chairman, supply officer | MVS | 15000 | PTA
|  |  | Acomplishing the ACR | Project Chairman | MVS | NC

## GOVERNANCE wathch
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
WATCH PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Pro- Watch- Catch- Match | Promote punctuality among teachers and employees from 50 to 55 in 2019 | 2 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Discussing the importance of Project WATCH in a meeting | All teaching and non-teaching personnel | MVS | NC
|  |  | Procuring materials for the construction of Attendance Monitoring Board | Supply Officer, Administrative Officer | MVS | 5000 | MOOE
|  |  | Understanding the value of punctuality | All teaching and non-teaching personnel | MVS | NC
|  |  | Upgrading biometrics to register time in and out of daily attendance correctly | Biometrics in-charge | MVS | NC
|  |  | Checking of teachers and employees registry | Biometrics in-charge | MVS | NC
|  |  | Accomplishing the ACR | Biometrics in-charge | MVS | NC

## GOVERNANCE MOOE UTILIZATIO
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
MOOE Utilization
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
MOOE Utilization | The school utilities and supplies will be catered of the MOOE fund from 70% to 100% by 2019 | 10% | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Prioritizing payments of the following: | School head and supply officers | MVS |  | MOOE
|  |  | a. monthly water bills |  | MVS | 195000
|  |  | b. monthly electrical bills |  | MVS | 200000
|  |  | c. monthly internet connection |  | MVS | 72000
|  |  | Sending teachers to trainings | School head | MVS | 300000 | MOOE
|  |  | Allocating funds for travel expenses | School Bookkeeper |  | 100000 | MOOE
|  |  | Purchasing office supplies and materials including gasoline for the vehicle per travel | Supply Officer |  | 520000 | MOOE
|  |  | Procuring printer for different department and sound system |  | MVS | 70000
|  |  | Preparing and submitting liquidated reports | Supply Officer and Disbursing officer |  | NC
Project Title: MOOE Utilization
Problem Statement: Only 70% of school utilities and supplies being catered of the MOOE fund
Project Objective Statement: By 2019, 100% of the school utilities and supplies will catered of the MOOE fund
Root Cause: Insufficient funds
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 | Teachers, School Head, stakeholders | NC
Prioritizing payments of the following: | Paid school utility bills | Year round | School head and supply officers |  | MOOE
a. monthly water bills |  |  |  | 195000
b. monthly electrical bills |  |  |  | 200000
c. monthly internet connection |  |  |  | 60000
Sending teachers to trainings | Sent teachers to trainings | Year round | School head | 300000 | MOOE
Allocating funds for travel expenses | Allocated funds for travel expenses | Year round | School Bookkeeper | 100000 | MOOE
Purchasing office supplies and materials | Purchased office supplies and materials | Year round | Supply Officer | 520000 | MOOE
Creating bidding awards committee | Created bidding awards committee | Year round | School head | NC
Preparing and submitting liquidated reports | Prepared and submitted liquidated reports | Year round | Supply Officer and Disbursing officer | NC

## GOVERNANCEsir monthly report
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
Monthly Accomplishment Report
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Monthly Accomplishment Report | Prepare 10 monthly accomplishment report in one School year | 10 | Monitor Schhool activities daily | Principal | MVS | 1000 | MOOE
|  |  | Supervise and observe classes | Principal | MVS | 1000 | MOOE
|  |  | Implement school PAP's , liquadate MOOE | Principal | MVS | 5000 | MOOE
|  |  | Conduct school conferences | Principal | MVS | 1000 | MOOE
|  |  | Prepare and submit ORS and MAR every Month with identified problems/ solutions | Principal | MVS | 1000 | MOOE
Project Title: Monthly Accomplishment Report
Problem Statement: Made prepare monthly accomplishment report
Project Objective Statement: Prepare 10 monthly accomplishment report in one School year
Root Cause: Identify problems and provide alternative met every month.
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Monitor Schhool activities daily | Daily Checklist | 2017-06-01 | Principal | 1000 | MOOE
Supervise and observe classes | Supervisory plan, report and TCOR | 2017-06-01 | Principal | 1000 | MOOE
Implement school PAP's , liquadate MOOE | List of School PAP,s , MOOE Report | 2017-06-01 | Principal | 5000 | MOOE
Conduct school conferences | Note, minute, attendance pictorials | 2017-06-01 | Principal | 1000 | MOOE
Prepare and submit ORS and MAR every Month with identified problems/ solutions | ORS and MAR Report | 2017-06-01 | Principal | 1000 | MOOE
Prepared by:
FRANCISCO B, LATORRE
School Principal I

## GOVERNANCE MULTI MEDIA PROGRAM
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
MULTI- MEDIA PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Multi- Media Program | Increase the number of functional LCD Projector for instruction through solicitations /donations from stakeholders from 2 to 5 | 1 | Communicating project team and parent | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | PTA prepare solicitation letter | Linkage coordinator | MVS | NC
|  |  | Implement the project on the solicited amount | Subject Teachers | MVS
|  |  | Making teaching-learning strategy more effective to students thru multi-media presentations Ex. TV set/Projector | School Head, Budget Officer | MVS | 25,000 (15,000) (5,000) (5,000) | PTA Donation other external stakeholder
|  |  | Increase students participation in classroom activity using film viewing and DVD Presentation | Teachers and Students | MVS | 2000 | MOOE
|  |  | Acomplishing the ACR | Project Chairman | MVS | NC

## GOVERNANCE LAND TITLING
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
TAX DECLARATION PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
TAX DECLARATION PROGRAM | Secure tax declaration of the school lot by 0 to 1 in 2019 | 1 | Communicating project team | Teachers, School Head, stakeholders | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Inquiring the documents necessary for school lot titling | Supply officer, School Head | Municipal Hall of Merida | NC
|  |  | Budgeting t for the school titling | Supply officer, School Head | MVS | 10000 | MOOE
|  |  | Requesting support from LGU and PTA | Linkage coordinator | MVS | NC
|  |  | Acquiring tax declaration from the Assessor's office | Supply officer, School Head | Municipal Hall of Merida | 2500 | MOOE
|  |  | Preparing and submitting liquidated reports | Disbursing officer | MVS | NC

## GOVERNANCEaip review
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
AIP REVIEW
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
LOVE ( Letting Others View and Empowered) | Increase the percentage of accomplishment of the programs and projects in E-SIP from 75% to 95% in 2019 | 8.3% | Communicating to the School Planning Team | School Head | MVS | NC
|  |  | Review the E-SIP to determine the unaccomplished programs and projects | School Planning Team | MVS | 1000 | MOOE
|  |  | Planning for the enhancement of the E-SIP | School Planning Team | MVS | 1000 | MOOE
|  |  | Finalizing and presenting the E-SIP to the stakeholders | School Head | MVS | 2000 | MOOE
|  |  | Submitting the E-SIP to SDS for approval | School Head | MVS | 500 | MOOE
|  |  | Implementing / accomplishing the programs and projects | Project Chairman and Co- chairman | MVS | 1000 | MOOE
|  |  | Monitoring and Evaluating the E-SIP | Project Chairman and Co- chairman | MVS | 1000 | MOOE
|  |  | Accomplishing the ACR | Project Chairman and Co- chairman | MVS | 1000 | MOOE
Project Title: LOVE ( Letting Others View and Empowered)
Problem Statement: 25% or 10 out of 39 programs and projects are not accomplished
Project Objective Statement: 95% of the program and projects in E- SIP would be accomplished in 2019
Root Cause: unaccomplished programs and projects in E-SIP
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating to the School Planning Team | Sent Communication | 2017-04-01 | School Head | NC
Review the E-SIP to determine the unaccomplished programs and projects | Reviewed SIP | 2017-04-01 | School Planning Team | 1000 | MOOE
Planning for the enhancement of the E-SIP | Enhanced E- SIP | 2017-04-01 | School Planning Team | 1000 | MOOE
Finalizing and presenting the E-SIP to the stakeholders | Finalized and Presented E-SIP | 2017-05-01 | School Head | 2000 | MOOE
Submitting the E-SIP to SDS for approval | roved E-SIP | 2017-05-01 | School Head | 500 | MOOE
Implementing / accomplishing the programs and projects | Accomplished programs and projects | 2018-03-01 | Project Chairman and Co- chairman | 1000 | MOOE
Monitoring and Evaluating the E-SIP | Monitored and Evaluated E-SIP | 2018-05-01 | Project Chairman and Co- chairman | 1000 | MOOE
Accomplishing the ACR | Accomplished ACR | 2018-05-01 | Project Chairman and Co- chairman | 1000 | MOOE

## GOVERNANCESAFETY AND SECURIY PR
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
SAFETY AND SECURITY PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Perimeter Fence | Construct perimeter fence from 75% to 100% in 2019 | 8.3% | Communicating to the Stakeholders | School Head | MVS | NC
|  |  | Organizing project team | School Head, Department Heads | MVS | 1000 | MOOE/ PTA
|  |  | Making a resolution to construct a perimeter fence through the PTA | PTA Officers | MVS | 300 | MOOE
|  |  | Submitting resolution for approval in the higher office | School Head | MVS | 500 | MOOE
|  |  | Constructing the Perimeter fence | School Head | MVS | 500000 | Donations/ PTA
|  |  | Monitoring and Evaluating of the PF | Project Chairman and Co- chairman | MVS | 1000 | MOOE
|  |  | Accomplishing the ACR | Project Chairman and Co- chairman | MVS | 1000 | MOOE

## GOVERNANCEPATHWAYS
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
PATHWAYS CONSTRUCTION PROGRAM
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Pathways Construction | Construct pathways from 50% to 100% in 2019 | 16.6% | Communicating to the Stakeholders | School Head | MVS | NC
|  |  | Organizing project team | School Head, Department Heads | MVS | 1000 | MOOE/ PTA
|  |  | Making a resolution to construct pathways through the PTA | PTA Officers | MVS | 300 | MOOE
|  |  | Submitting resolution for approval in the higher office | School Head | MVS | 500 | MOOE
|  |  | Constructing the pathways | School Head | MVS | 100000 | Donations/ PTA
|  |  | Monitoring and Evaluating of the pathways | Project Chairman and Co- chairman | MVS | 1000 | MOOE
|  |  | Accomplishing the ACR | Project Chairman and Co- chairman | MVS | 1000 | MOOE

## charm record mamangement
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
Classroom and Record Management
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
CHARM ( Classroom for Harmony and Accurate Record Management) | Reduce the number of teachers with satisfactory classroom and record management from 9 to 0 by 2019 | 2 | Communicating Project team and School Planning team | School Heads, School Planning tean and Prject Team | MVS | NC
|  |  | Organizing project team and School Planning team |  | MVS | 1000 | MOOE/ PTA
|  |  | Planning for the schedule of classroom Evaluation and Record Management | School Heads. PTA and SGC | MVS | 1000 | MOOE/ PTA
|  |  | Submitting reports regarding the Evaluation results | School Heads. PTA and SGC | MVS | 100 | MOOE
|  |  | Waiting for the 24 classrooms to be finished | School Heads, School Planning team | MVS | NC
|  |  | Tranferring of teacher- adviser from grade 7- 10 to the newly constructed building | School Heads, School Planning team | MVS | NC
|  |  | Accomplishing the ACR | Project Chairman and Co- chairman | MVS | NC | MOOE

## help lesson planning tchnical )
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
Technical Assistance of Daily Lesson Plan Preparation
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
HELP ( Helping to Enhance Lesson Planning) | Reduce the no. of teachers who are delayed in submitting lesson plans from 11 to 1 in 2019 | 2 | Communicating Project team | School Heads, Project Team | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Planning for the schedule of giving technical assistance | School Heads, Project Team | MVS | NC
|  |  | Providing Technical assistance |  | MVS | NC
|  |  | Accomplishing the ACR | Project Chairman and Co- chairman | MVS | 100 | MOOE

## sosa
ANNUAL IMPLEMENTATION PLAN 2018
GOVERNANCE |  | Priority Improvement Areas (PIAs)
Statement of School Address (SOSA)
Project Title | Project Objective | Output for the Year | Activity/ies | Person Responsible | Venue | Budget per activity | Budget Source
Statement of School Address (SOSA) | Increase the number of SOSA held from 3 to 6 by 2019 | 1 | Communicating Project team | School Heads, Project Team | MVS | NC
|  |  | Organizing project team |  | MVS | NC
|  |  | Planning for the schedule in conducting SOSA | School Heads, Project Team | MVS | NC
|  |  | Communicating the PAPs coordinators and other stakeholders |  | MVS | NC
|  |  | Accomplishing the ACR | Project Chairman and Co- chairman | MVS | 100 | MOOE