## ENROLMENT
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Enrolment
Problem Statement: 80 students not enrolling for the last 2 years
Project Objective Statement: Increase enrolment from 1040 to 1,200 from Grade 7 to Grade 10 in 2020
Root Cause: Distance from home to school
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent communication | First Quarter | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | First Quarter | Teachers, School Head, stakeholders | NC
Conducting Oplan - Balik Eskwela campaign | Compiled MOV's for "Oplan Balik Eskwela" | May | Teachers, School Head, stakeholders | 1000
Identifying intervention programs to fit the need of the learner | Identified intervention programs | May | Teachers, School Head, stakeholders, Project BEST Coordinator | NC
Monitoring of Students attendance | Compiled Students' attendance | Year round | Teachers Adviser | NC
Intensifying "Project BEST " | Actual Completion report of the Project BEST | Year round | Project BEST Coordinator | NC
Giving of awards to "Balik- Eskwela" highest achievers and advisers | Awarded achievers and advisers in "Balik Eskwela" | Last Quarter | Teachers, School Head, stakeholders, Project BEST Coordinator | 2000 | MOOE
Acomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 |  | NC
Prepared by:
DIVINA B. SANCHEZ |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## no. of drop outs
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: SAKAY NA- LIBRE PA
Problem Statement: 92 out of 1081 enrolles who are identified as SARDO
Project Objective Statement: Save 92 SARDO students to sustain zero- drop out by 2020
Root Cause: Distance to school
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent communication | June , 2019 | Teacher- Adviser, Guidance Counselor, stakeholders, School Principal, Project BEST coordinator | NC
Organizing project team | Organized project team | June , 2019 |  | NC
Identifying SARDO students | Identified top 10 SARDO students | June , 2019 |  | NC
Preparing of Program design to answer SARDO need | Project work Plan And Budget Matrix | June , 2019 |  | NC
Preparing of MOU with parents and program sponsor | Signed MOU | June , 2019 | Project BEST Coordinators, School Principal, parents, stakeholders/ program sponsor | 500 | PTA
Hiring School Driver to run the school service for the students to ride to and fro with a free fare. | Hired Regular School Driver | July, 2017 | DORP Coordinator, School Head, Administrative Officer | NC
Looking for sponsoring group to maintain and supply the School's Service needs. | Identified Sponsoring group | July, 2017 | DORP Coordinator, Linkage Coordinator, School Head, Administrative Officer | NC
Budgeting the needs for the School Service (Fuel, other maintenance) | Budgeted needs of the school service | July, 2017 | DORP Coordinator, Supply officer, School Head, Administrative Officer | 70000 | MOOE/ PTA/ Business Partners
Implementing the program to save SARDO | Compiled implemented program | June , 2019 | Project BEST Coordinators, School Principal, parents, stakeholders/ program sponsor | 4800 | PTA
Monitoring the attendance of SARDO student's performance | Compiled attendance of SARDO student's | Year round |  | 500 | PTA
Awarding of save SARDO as completers | Awarded save SARDO as completers | Year round | School Head, supply officers | 2000 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman and Co- chairman | NC
Prepared by:
ELMER GARCIANO |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## acces save sardCULTURE AND ARTS
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Talento MO- Pag-agak KO (School-Based Adopt-A-Student Program)
Problem Statement: Inadequate number of available costumes in the MVS PAG Organization
Project Objective Statement: Procure 10 sets of costumes for MVS PAG Organization in 2020
Root Cause: Insufficient budget intended for costumes
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June | Teachers, School Head, stakeholders | NC
Organizing PAG to develop singing, dancing, and acting skills of students | Maintained PAG activities | Year round | MAPEH Teachers | 5000 | Club Funds/Personal Donations
Assigning MAPEH teacher to handle the group |  | Year round |  | 5000 | PTA
Purchasing materials for costume production | Produced costumes | Dec- Jan | MAPEH Teachers, supply officers | 10000 | PTA
Participating during monthly culmination | Produced costumes for every presentation | Year round | MAPEH Teachers and students | 1000 | MOOE
Implementing annual cultural production in the school (PAG Recital) | Conducted Pag Recital | Year round | MAPEH Teachers and PAG Members/ students
Conducting Fund raising activities through PAG Recital Show for the Club to support the Adopt-a-student- program | Conducted Pag Recital Show | 2018-03-01 | DORP Team, MAPEH Teachers and PAG Members/ students | 5000 | Club Funds/Personal Donations
Liquadating the expenses | Liquadated reports/ financial Report | Year round | MAPEH Teachers and PAG Members/ students | NC
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman | NC
Prepared by:
NESTOR A. CASTAÑOS Jr. |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## incidence of tardiness
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: HASHTAG ( Help Achieve High performance Teacher Assistance Group)
Problem Statement: 120 out of 1048 students from grade 7 to 10 are habitually cutting classes
Project Objective Statement: Reduce number of students habitually cutting classes to 50 out of 120 by 2020
Root Cause: Distance to school
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Crafting of the Modified checklist | School – based daily monitoring checklist | At home April-May | Teachers | 500 | MOOE
Checking of the daily attendance in all subjects | Compiled attendance sheets | School May- June | Teachers | 500 | MOOE
Consolidating the result | Consolidated results | June to March | Teacher | 500 | MOOE
Analyzing and sending letters to parents | Compiled checklist with analysis | June - March | Department Head | NC
Adopting a student through SAKAY NA- LIBRE PA Program | List of identified students | June, 2019 | HASHTAG Coordinator, Advisers, School Head | NC
Compiling the monthly student’s attendance and agreement with parents | Compiled monthly student’s attendance and agreement with parents | June- March | Guidance advocate | NC
Acomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman and Co- chairman | NC
Prepared by:
RUJYN O. MONARES |  |  | RAUL G. ITCHON
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## habitual absenteesim
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Bahay Sa Paaralan ko Pansamantalang Tirahan KO
Problem Statement: 248 out of 1081 enrollees who have incidence of habitual absenteeism
Project Objective Statement: Reduce number of enrollees with incidence of habitual absenteeism from 248 to 50 by 2020
Root Cause: Geographical location from home to school.
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parents | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Conducting Demographic profile per student | Compiled demographic profile | June | All Adviser | 500 | MOOE
Submitting of identified students habitually absent | listed learners with incidence of Habitual Absenteeism | June | Teacher Adviser | NC
Conducting meeting with the parents for the construction of Temporay Shelter for Students inside the Campus for those who live in far flung barangays | Minutes, attendance | July | PTA, School Head, All MVS Personnel | 1000 | MOOE
Signing of MOU construction of Temporay Shelter of Students inside the Campus for those who live in far flung barangays | Approved MOU | August | PTA, School Head, All MVS Personnel | 1000 | MOOE
Budgeting the needs for construction of Temporay Shelter of Students inside the Campus for those who live in far flung barangays | Budget Plan | August | Supply officer, School Head, Administrative Officer | NC
Canvasing and Purchaing the materials needed | Purchased materials | August | Supply officer, School Head, Administrative Officer | 50000 | PTA/MOOE/ Alumni
Submitting Liquadation reports | Submitted Liquadation reports | September | Supply officer, School Head, Administrative Officer | NC
Acomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman and Co- chairman | NC
Prepared by:
IAN EINSTEIN O. DIGMAN |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## NUTRITIONAL STATUS
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Pagkain Alagaan, Timbang dagdagan
Problem Statement: 15 students are severely wasted in MVS
Project Objective Statement: Decrease the number of severely wasted students from 15 to 0 in 2020
Root Cause: Poor dietary habit
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June , 2019 | Teacher- Adviser, School Nurse, Guidance Counselor, Coordinators, School Principal | NC
Organizing project team | Organized project team | June , 2019 |  | NC
Identifying the severely wasted students | Identified severely wasted students | June , 2019 | Teacher- Adviser, School Nurse, Guidance Counselor, Coordinators, School Principal | 500 | MOOE
Conducting Orientation Related to Proper Health Diet | Conducted orientation | 2019-07-01 |  | 2000 | PTA
Feeding Program for the identified severely wasted students during monthly celebration | Compiled Checklist of students undergone Feeding Program | July - Dec. 2019-2020 | Teacher- Adviser, School Nurse, Guidance Counselor, Coordinators, School Principal | 12500 | PTA
Monitoring and Evaluation of the Project Design | Monitored and evaluated activity | July - Dec. 2019-2020 | SMEA | 1500 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project chairman and co-chairman | NC
Prepared by:
DIVINA B. SANCHEZ |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## Reading AbilityIRP
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Improved Reading Program (IRP)
Problem Statement: 118 out of 1081 students are in the Frustration Level
Project Objective Statement: Reduce number of students in frustration Level from 118 to 0 in 2020
Root Cause: less interest in reading
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parents | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 | Teachers, School Head, stakeholders | NC
Conducting an institutionalized Reading Assessment/Inventory to students using a standardized test/teacher made test | Reduced frustration of level of non-readers. | 1st week of June 2019 | English/ Reading Teachers | 2000 | MOOE
Identifying and enlistment of non-reader students/project beneficiaries based on the test result | Identified non-reader students/project beneficiaries | 1st week of June 2019 | English/Reading Teachers | NONE
Communicating of test results and proposed project to internal and external stakeholders concerned through a conference meeting |  | 2nd week of June 2019 | SH, Dept. Head /Teachers | NC
Establishing and organizing of reading team composed of teachers | Organized Reading teams for Teachers | 2nd week of June 2019 | SH, Dept. Head /Teachers | NC
Evaluating of Reading Teachers’ Pedagogical Skills, Content, Knowledge on the Teaching of Reading using a survey questionnaire | Zero-out identified non-readers or at risk -readers | 2nd week of June 2019 | Reading Team/Teachers | 100 | MOOE
Conducting of an INSET on Teaching Reading | Attended the INSET on Teaching Reading | 3rd week & 4th week of June 2019 | SH. Reading Team/Teachers | 10000 | MOOE
Crafting of Development Reading Intervention Program: Gathering of instructional inputs/reading materials , Production/ Construction of instructional inputs /reading materials | Crafted the Developmental Reading Intervention | 3rd & 4th week of June 2019 | SH, and Reading Team/Teachers | 30000 | MOOE
Provisioning varied and appropriate reading materials in the said Reading Room/Center | Organized reading centers | June | Reading Teachers | 4000 | MOOE
Preparing schedule for the intervention program implementation
Establishing and organizing Reading Club composed of students in the pilot classes or student achievers | Organized Reading Club | 4TH week of June 2019 | Reading team/ Teacher and students | NC
Conducting workshop on doing individualized Reading Tutorial for student reading buddies | Top ten (10) performing students attended the workshop on tutorial reading | 4th week of June | Reading Team/ Teachers and Reading Club | 5000 | MOOE
Implementing actual Intervention program | Implemented actual Reading intervention | July - Oct | Student beneficiaries/Teachers | 5000 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman and Co- chairman | NC
Prepared by:
ELINETA T. PERALES |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## nUMERACY LEVEL I LOVE MATH
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: I LOVE MATH Program
Problem Statement: Higher number of enrollees classified as poor in terms of performance in Mathematics
Project Objective Statement: Decrease the number of students classified as poor in terms of performance in Mathematics from 217 to 50 in 2020
Root Cause: Cutting classes/ Absenteeism
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 | Teachers, School Head, stakeholders | NC
Identifying students with difficulties in certain Mathematical Concept | Identified low learners' in Mathematics | 2017-06-01 | Mathematics Teachers | NC
Peer tutoring during ICL | Visible increased in the MPS in every quarter examination | ICL Period | Mathematics Teachers | 1000 | MOOE
Giving of specialized activities to identified students with difficulties in certain Mathematical concept | Specialized activities | Whole Year Round | MATH CLUB OFFICERS and Members | 1000 | MOOE
Empowering advanced students to mentor peers. | Empowered advance students to mentor peers | Whole Year Round | Students | 1000 | MOOE
Monitoring and evaluating students' performances in Mathematics | Checklist of Monitored Students | Whole Year Round | Mathematics Teachers | NC
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman and Co- chairman | NC
Prepared by:
Prepared by:
JURALENE C. BARREDO |  |  | KISLEV CHARM L. TRAVERO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## PROJECT BEST
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Project BEST (Barangay Education Strategic Team)
Problem Statement: Unsustained 100% promotion rate
Project Objective Statement: by 2020, promotion rate will increase from 95.35% -100%
Root Cause: distance from home to school
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 | Teachers, School Head, stakeholders | NC
Conducting a Quarterly meeting with the Project BEST members. | Conducted meetings in relevance to saving SARDO | Quarterly | Principal, Project BEST Coordinator, Barangay Council | 5000 | MOOE
Monitoring students who are at risk of Dropping out (SARDO) | Monitored SARDO ( Drop out Rate, Cohort Survival Rate and Completion Rate) | Weekly/ Monthly | Class Adviser, Project BEST Coordinator, Barangay Council | 4000 | MOOE
Awarding of stakeholders who have an exemplary contribution to the success of the program | Stakeholders given recognition of their prolific contribution to the program | 2018-03-01 | Principal, School-Based Awards and Recognition Committee,Project BEST Coordinator | 1000 | MOOE
Accomplishing ACR | Accomplished ACR with supported MOV's | Quarterly | Project Chairman and Co- Chairman | NC
Prepared by:
MIGUEL G. COVERO JR. |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## MATH (2)
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: MATHEMATICS ADVANCE TUTORING ON HIGHLY-DEVELOPED LEARNERS Program (MATH-DLP)
Problem Statement: 33% of the Mathematics contestant who participated in the Division Math contest where able to achieve Top 3 spots.
Project Objective Statement: by 2020, 66% of the students who participated in the Division Math contest can achieve the Top 3 spots.
Root Cause: To qualify for Regional and National competitions
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | 1, 000 | MOOE
Organizing project team | Organized project team | 2017-06-01 | Teachers, School Head, stakeholders | 1, 000 | MOOE
Identifying potential learners to be part of the MATH-DLP | Awarded as TOP Winners | 2017-06-01 | Mathematics Teachers | 5000 | MOOE
Conducting specialized training and review on potential learners. | Conducted specialized training | June- March | Students | 5000
Participating MATH Quiz and MTAP DepED Math Challenge | Participated MATH Quiz and MTAP Challenge | October, January & February | School Head, Supply Officer | 15000
Accomplishing the ACR | Accomplished ACR with supported MOV's | Year round | Project Chairman and Co- Chairman | 1, 000 | MOOE
Prepared by:
JOEVEN A. GLORIA |  |  | NIÑA ROSARIO RAÑOLA
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## quality non aca technolympics
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: TECHNOLYMPICS
Problem Statement: 2 out of 13 skills able to participate in the Division Technolympics
Project Objective Statement: Increase number of participation in different skills from 2 to 8 in 2020
Root Cause: Lacking of proper training for identified participants
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Set Communication | June | Teachers, School Head, Stakeholders | NC
Organizing project team | Organized project team | June | Teachers, School Head, Stakeholders | NC
Identifying potential students to be part of the Technolympics Competition | Identified potential competitors to be part of the Technolympics Competition | June | STVE Teachers | NC
Planning and Budgetting training programs for Technolympics parcticipants | Workshops/Training Design | June | STVE Teachers, Coach | 2000 | STVE Funds
Procuring of supplies and facilities for the proper training | Procured supplies and facilities | Year round | STVE Teachers, Coach, supply officer | 50000 | STVE Funds/ MOOE
Conducting specialized training on different skills to be participated in the Technolympics Competition | ACR, and Narrative Report | July | STVE Teachers, Coach | 500 | STVE Funds/ MOOE
Participating in the Technolympics Competition | ACR, Narrative Report, Certificates and Communication Letters | September 2019-March 2020 | STVE Teachers, Coach | 15000 | STVE Funds/ MOOE
Accomplishing the ACR | ACR with supported MOV's | July - December 2020 | STVE Coordinator | NC
Prepared by:
GEMMA P. CAMINERO |  |  | GILBERT C. TRAVERO
Project Chairman |  |  | Project Co-Chairman
Approved:
FRANCISCO B. LATORRE
School Principal II

## JOURNALISM
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: The Meridian - Journalism
Problem Statement: School's Journalism Contest results are up to Division Level. Thus, the publication aims to participate to higher competitions (Regional and National).
Project Objective Statement: Develop 40 young journalists to compete in the higher academic competition by 2020.
Root Cause: Lacking of proper training for identified potential writer.
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Set Communication | June | Teachers, School Head, Stakeholders | NC
Organizing project team | Organized project team | June | Teachers, School Head, Stakeholders | NC
Identifying potential students to be part of the JOURNALISM | Identified potential competitors to be part of the JOURNALISM | June | English Teachers and School Pub. Adviser | NC
Planning and Budgetting training programs for CAMPUS JOURNALISM | Workshops/Training Design | June | School Pub. Adviser and Editorial Staff | 2000 | School Pub. Funds
Procuring of facilities for radio broadcasting and TV Newscasting | News Room (Radio Broadcasting and TV Newscasting) | Year round | School Pub. Adviser, Editorial Staff and PTA | 250000 | LGU, Alumni, School Pub. Funds
Conducting specialized training on writing, radio broadcasting and TV newscasting to identified potential competitors. | ACR, and Narrative Report | July | School Pub. Adviser and Editorial Staff | 7000 | School Pub. Funds
Participating in School's Press Conferences | ACR, Narrative Report, Certificates and Communication Letters | September 2017-March 2018 | School Pub. Adviser and identified competitors | 60000 | School Pub. Funds
Production of Tabloid - The Meridian | Tabloid | October | School Pub. Adviser and Editorial Staff | 25000 | School Pub. Funds
Monitoring and Evaluation of the Project Design | Monitored and Evaluated Activity | July - December 2020 | SMEA and School Pub. Adviser | 1500 | MOOE
Accomplishing the ACR | ACR with supported MOV's | July - December 2020 | School Pub. Adviser and Editorial Staff | NC
Prepared by:
MYRON JOSHUA C. DELGADO |  |  | NIÑA ROSARIO RAÑOLA
Project Chairman |  |  | Project Co-Chairman
Approved:
FRANCISCO B. LATORRE
School Principal II

## school pasidungog
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: School-based Awards and Recognition System
Problem Statement: Only 6% of the MVS teachers are recognized in the Division PASIDUNGOG
Project Objective Statement: by 2020, at least 11% of the MVS teachers will be recognized in the Division PASIDUNGOG
Root Cause: School-based Awards and Recognition nomination guidelines were implemented in the later part of the school year
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating and organizing SAR project team | Communication Letters/ Organized SAR project team | 2017-06-01 | School Heads, faculty and stakeholders | NC
Reviewing of the School-based Pasidungog Nomination Guidelines | Revised School-based Pasidungog Nomination Guidelines | 2017-07-01 | SAR project team/ Assessment committee | 2000 | MOOE
Orienting MVS faculty and stakeholders on the nomination guidelines | Defined roles and responsibilities on the given guidelines | 2017-07-01 | SAR project team/ Assessment committee/ Faculty/ Stakeholders | 500 | MOOE
Selecting of MVS faculty nominees | Roster of the School-based Pasidungog teacher nominees | 2017-11-01 | SAR project team/ Assessment committee | 2000 | MOOE
Selecting of MVS stakeholders nominees | Roster of the School-based Pasidungog stakeholder nominees | 2018-01-01 | SAR project team/ Assessment committee | 2000 | MOOE
Validating of the School-based Pasidungog nominees | Roster of the qualified School-based Pasidungog candidates | 2018-02-01 | SAR project team/ Assessment committee | 500 | MOOE
Awarding of the outstanding School-based Pasidungog candidates | Roster of the School-based Pasidungog awardees/ Certificates | 2018-03-01 | School Heads, SAR project team, faculty and stakeholders | 5000 | MOOE
Assessing the conducted activities | ACR/ Narrative Reports/ Evaluation Results | 2018-03-01 | SAR project team | 500 | MOOE
Prepared by:
BERNLEY JOY M. NOBLEZA |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## filipino 1
ANNEX 9 Project Work Plan and Budget Matrix
Pamagat ng Proyekto: Kumprehensibong Programa sa Pagbasa
Pagpahayag ng Suliranin: 52 ng mga mag-aaral sa Baitang 10 ay nasa kabiguang antas
Layunin ng Proyekto: Maipababa ang antas ng kabiguan sa pagbasa sa mga mag-aaral sa baitang 10 mula 52 patungo sa 12
Pangunahing Dahilan: Pagliban sa Klase
Project Work Plan and Budget Matrix
Gawain | Awtput | Petsa ng pagsagawa | Mga taong Responsible | Budget | Pagkukunan ng Budget
Pakikipag-ugnayan sa pangkat at mg magulang | Nakapadala ng liham | Hunyo 2019 | Guro, Punong-guro, stakeholders | NC
Pagbubuo ng pangkat ng Taga-pangasiwa | Nakabuo ng pangkat at taga-pangasiwa | Hunyo 2019 | Guro, Punong-guro, stakeholders | NC
Pagsasagawa ng pagpupulong sa pagbasa (Pagkukuwento at muling pagkukuwento) | Naisagawa ang pagpupulong sa pagbasa (pagkukuwento at muling pagkukuwento) | Dalawang beses sa isang buwan | Guro, Mag-aaral sa baitang 10 | 1000 | MOOE
Pagbili ng SMART TV para sa Filipino asignatura | Nakabili ng SMART TV | Agusto 2016 | Guro, stakeholders | 30000 | PTA - Filipino Klab
Pagsagawa ng "Film Showing" | Naisagawa ang "Film Showing" | Isang beses sa isang linggo | Guro, Mag-aaral | 1000 | MOOE
Pagsagawa ng "Summative Test" | Nasuri ang mga mag-aaral | Quarterly | Guro, mag-aaral | NC
Pagsagawa ng ACR | Naisagawa ng ACR na may MOV's | Quarterly | Project chairman and co- chairman | NC
Inihanda:
MARILYN A. CANILLO |  |  | CHONA M. LABADOR
Project Chairman |  |  | Project Co-Chairman
Ipinagtibay:
FRANCISCO B. LATORRE
School Principal II

## SPORTS arnis)
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: MVS ARKADO (Arnis-Kali-Do)
Problem Statement: Only 10% of the MVS ARKADO team participated in the EVRAA Meet
Project Objective Statement: by 2020, at least 30% of the MVS ARKADO team will participate in the EVRAA Meet
Root Cause: Appropriate facility and equipment for Arnis trainings is highly needed
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating, organizing and staffing MVS ARKADO Club | Communication Letters/ Parent's Permit/ MVS ARKADO Organizational structure | 2017-06-01 | ARKADO Club Advisers/ Officers/ Members | Php 500.00 | MOOE/ PTA
Planning and Budgeting Training Programs (Arnis Sports facility and equipment) | Arnis Training Program Design/ Training Matrix | 2017-06-01 | School Heads/ Arnis Coach&Trainer/ Stakeholders | Php 143, 000.00 | MOOE/ PTA/ LGU
Conducting Arnis Sports Clinic | Communication Letters/ Program Matrix/ Training Kits/ Certificates/ Tarpaulin/ ACR/ Narrative Reports | 2017-07-01 | School Heads/ Arnis Coach&Trainer/ Student Athletes/ Stakeholders | Php 2, 000.00 | MOOE/ PTA/ LGU
Participating Arnis Competitions in Athletic Meets | Communication Letters/ Transparency Reports/ Certificates/ ACR/ Narrative Reports | August 2019 - February 2020 | School Heads/ Arnis Coach&Trainer/ Student Athletes/ Stakeholders | Php 25, 000.00 | MOOE/ LGU/ PTA
Awarding and Promoting MVS ARKDO Club members | Communication Letters/ Certificates/ ACR/ Narrative Reports | 2018-03-01 | School Heads/ MVS ARKADO Coach&Trainer/ Members/ Stakeholders | Php 1, 500.00 | MOOE/ PTA
Assessing the conducted activities | Communication Letters/ ACR/ Narrative Reports/ Evaluation Results | 2018-03-01 | School Heads/ Arnis Coach&Trainer/ Student Athletes/ Stakeholders | Php 500.00 | MOOE/ PTA
BERNLEY JOY M. NOBLEZA |  |  | AMOR ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## SPORTS
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: MVSports "ABAG" Program
Problem Statement: Decrease promotion rate of SY 2019-2020
Project Objective Statement: by 2020, promotion rate will increase from 95.35% -100%
Root Cause: Lack of interest and poor study habit
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Sports Coordinator,Chairman, Co-Chairman Coaches, Trainers, and Athletes | NC
Organizing sports club and encouraging students ( specially SARDO) to be part of any sports they felt could develop them holistically | Organized sports club and members are benefited to the earnest and holistic transformation each sports discipline entails | 2017-06-01 |  | NC
Attending training and seminars to be constantly updated of the, rules and regulations, and new sports trends | Coaches constantly updated of the new trends, rules and regulations through trainings, seminars, and delved respective events | As needed | Sports Coordinator, Coaches, Trainers, and Athletes | 20000 | MOOE, Sports Fund
Adhering to the special training program/design prepared | Coaches and athletes tenaciously adhere the specials training program prepared | Always | School Head, Sports Coordinator, Coaches, Trainers, and Athletes | NC
Providing every active sports discipline with the necessary gears and equipment to be used for practice and game proper | Sports equipment and gears are supplied to the deserving sports discipine | Always | School Head, Supply Officer, Sports Coordinator, Coaches and Athletes | 200000 | MOOE, LGU, GPTA, Sports Fund
Organizing quarterly sports festival and compete in athletic meets | Active sports enthusiast participating and competing insports fest and athletic meets | After quarterly exam | School Head, Sports Coordinator, Coaches, Trainers, and Athletes | 15000 | MOOE, LGU, GPTA, Sports Fund
Close monitoring of each member's responsibilty and accountability particularly in balancing their sports with their academics | Assessed members needs and adressed them earnestly ASAP | Quarterly or as needed | School Head, Sports Coordinator, Teachers,Teacher-Adviser, Coaches, Trainers, and Athletes | NC |  | ..
Awarding of Sports club members, benefactors and stakeholders who have done exemplary performance and heartwarming contributions to success of the program | Sports club members and Stakeholders are given recognition of their prolific contribution to the program | 2018-03-01 | School Head, Sports Coordinator, Teachers,Teacher-Adviser, Coaches, Trainers, Athletes and stakeholders | 1000 | MOOE, Sports Fund | .
Giving incentives in cash to those athletes who are advancing for PALARONG PAMBANSA | List of Awardee (EVRAA Category) | 2018-03-01 |  | 80000 | MOOE/PTA/ LGU
Accomplishing the ACR | Accomplished ACR with supported MOV's | Year round | Sports Chairman | NC
Prepared by: |  |  |  | 316000
MIGUEL G. COVERO |  |  | EDELYN P. CAYCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## YES O
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: MVS YES-O CAMPERS - Batang Maka-agham, Pag-asa ng Kalikasan
Problem Statement: Less number of students participating in YES-O Camp and Eco- friendly activities
Project Objective Statement: Involve 70 of the 110 YES-O registrants in community and eco- friendly activities in 2020
Root Cause: Less technical assistance provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 | Teachers, School Head, stakeholders | NC
Regularly review class schedule to enrich and proficient students to participate in Science Quiz Bee | MVS YES-O Campers sustainably recognized the YES-O activities at division and Regional Level | June 2019 onwards | Science Teachers, YES-O Campers | 10000 | Science Club Fund
Organizing environmental program and encouraging community to be involved | Regular advocacy and participation of the environmental activities such as Tree Planting, Clean-Up Drive and the likes | Whole Year Round | MVS Community, LGU, NGO’s
Acomplishing the ACR | Accomplished ACR with supported MOV's | Year round | Project Chairman and Co- chairman | NC
Prepared by:
LEVINE EUGENE D. ANONAT |  |  | AMOR S, ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## GULAYAN
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Tanim ko - Ani ko
Problem Statement: Only 5% of the expected Gulayan sa Paaralan Program generated income is attained.
Project Objective Statement: by 2020, Gulayan sa Paaralan Program income generation will increase to 50%.
Root Cause: geographical location (flooded area)
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating and organizing project team and stakeholders. | Sent Communication and organized GPP project team. | 2019-06-01 | GPP Project Team, Stakeholders | 500 | MOOE
Planning and budgeting training programs for Gulayan sa Paaralan Program. | GPP Program Matrix | 2019-06-01 |  | 5000 | MOOE
Orienting the stakeholders about Gulayan sa Paaralan Program. | ACR , Narrative Report | 2019-06-01 | GPP Project Team | 200 | MOOE
Implementing the Gulayan sa Paaralan Program. . Securing seeds locally adapted vegetable varieties. .Preparing the garden soil. .Planting of vegetable variety. | Documentation, Attendance of Stakeholders | 01/06/2019 July 2019 | GPP Project Team | 2000 500 | MOOE
Weeding and cultivating. | Transparency |  | GPP Project Team | 500
Harvesting and marketing of the vegetables. |  | once a month | GPP Project Team | 500 | MOOE
Assessing the conducted activities. | Communication letters, ACR, Narrative Reports, Evaluation Reports | Quarterly | GPP Project Team | 500 | MOOE
Prepared by:
MARIBELLE T. PITAO |  |  | EMMA S. DONAYRE
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## SCOUTING
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: MVS Scouting Movement
Problem Statement: There are only 43 out of 488 BSP potential and 109 out of 560 GSP potential
Project Objective Statement: Increase number of members to 244 out of 488 BSP potential and 296 out of 592 GSP potential in 2020
Root Cause: Less technical assistance provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parents | Sent Communication | 2016-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2016-06-01 | Teachers, School Head, stakeholders | NC
Organizing scouting to improve the total personality of young students | Organizing scouting to improve the total personality of young students | Year round | MAPEH Teachers, Scouting coordinators | 10000 | PTA- Scouting Funds
Sending scouts/ coordinators for trainings | Sent scouts/ coordinators for trainings | September | MAPEH Teachers, Scouting coordinators | NC
Advancement of scouters/ providing awards/ merits for outstanding scouters | Provided awards/ merits for outstanding scouters | March | MAPEH Teachers, Scouting coordinators | 5000 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman and co- chairman | NC
Prepared by:
NESTOR A. CASTAÑOS JR. |  |  | GRACELYN V. MOJADO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## TEACHER PROMOTION
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: TEACHERS' PROFESSIONAL DEVELOPMENT PROGRAM
Problem Statement: Teachers do not enroll in graduate studies and lack teaching- related
Project Objective Statement: All teachers earn units in graduate studies and attend at least one teaching- related training in 2020
Root Cause: Technical assistance not provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project program's rationale and targets | Sent Communication | 2019-06-01 | Project Chairman, Teachers, School Head, stakeholders | NC
Re-visiting IPPD & update teachers' competency level | Updated the IPPD/ NCBTS –TSNA and determine teachers' competency level | July - Aug 2019 | Teachers Dept. Head, & SH | NC
Preparing individual professional development plan | Prepared individual professional development plan | 2017-09-01 | Teachers Dept. Head, & SH | NC
Identifying teachers' Strengths and Needs | Identified Strengths and Needs | 2017-09-01 | Project chairman | NC
Conducting INSET | Conducted INSET | 2017-10-01 | Teachers Dept. Head, & SH | 11500 | MOOE
Identifying teachers to attend the Division, Regional and National teaching- related trainings | Attended trainings related to teaching | whole year round | Teachers | 41250 | MOOE
Accomplishing the ACR | Accomplished ACR | Once a year | Project Chairman and Co- chairman
Note: Please record also the date of monitoring per activity Please attach this form to the AIP template
Prepared by:
KISLEV CHARM L. TRAVERO |  |  | ELPEDIO P. MABIYA
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## ASSESSMENT PROG
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: TESDA Standards - Graduates Standards
Problem Statement: SHS cannot secure NC from TESDA
Project Objective Statement: Assess 200 out of 230 SHS to secure NC from TESDA in 2020
Root Cause: No technical assistance provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2016-06-01 | Teachers, School Head, stakeholders | NC |  | Assessment Program | Improve performance of students in all subject areas and assessment initiated by TESDA
Organizing project team | Organized project team | 2016-06-01 | Teachers, School Head, stakeholders | NC
Identifying students to be assessed in TESDA | List of students for assessment | Quarterly | Teachers | 20000 | PTA Fund
Administering skill mastery trainings | Improved Assessment performance from 1st to 4th contact | Once a year | Department Heads/ Teachers | 6000 | PTA Fund
Conducting departmentalized assessment | Conducted School-Based assessment by specialization | Quarterly | Teachers | NC
Acomplishing the ACR | Accomplished ACR with supported MOV's | Year round | Project Chairman and Co- Chairman | NC
Note: Please record also the date of monitoring per project Please attach this form to the AIP template
Prepared by:
GILBERT C. TRAVERO |  |  | TERESITA L. MORIL
Project Chairman |  |  | Project Co-Chairman
Approved :
MANOLITA C. RUIZO
School Principal III

## DRRM
ANNEX 9 Project Work Plan and Budget Matrix
Project Title:MVS ERUF (Emergency Response Unit Force)
Problem Statement: Only 22% of the MVS community are capacitated for DRRM
Project Objective Statement: by 2020, 80% of the MVS community are capacitated for disaster risk reduction management before, during and after the occurrence of hazards.
Root Cause: Disaster risk reduction management preparedness is highly recommended
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating and organizing project team. | Communication Letters/ Organized SDRRM project team | 2018-06-01 | SDRRM Coordinator/ MVS Employees and Stakeholders | 500 | MOOE
Planning and Budgeting Training Programs for DRR Preparedness | Workshop/ Training Program Matrix | 2018-01-01 | SDRRM Project Team | 5000 | MOOE | n
Preparing Emergency Response Plan | Developed Emergency Response Plan/ School Development Plan Framework | 2018-01-01 | SDRRM Project Team | 1500 | MOOE/ PTA
Crafting of the School Contingency Plan | MVS DRRM Contingency Plan | 2018-01-01 | School Heads/ SDRRM Project Team | 1500 | MOOE
Procuring rescue equipment and other emergency paraphernalia | Procured rescue equipment and other emergency paraphernalia | 2018-05-01 | School Heads/ SDRRM Project Team | 100000 | MOOE/ LGU/ PTA
Procuring Hand held Radio | Procured Hand held Radio | 2018-05-01 | School Heads/ SDRRM Project Team | 50000 | MOOE/ NGO
Institutionalizing school additional Early Warning System | Additional Early Warning System | 2018-05-01 | School Heads/ SDRRM Project Team/ MVS Stakeholders | 18000 | MOOE/ NGO
Formulating of Evacuation Procedures | Formulated Evacuation Procedure | 2018-01-01 | School Heads/ SDRRM Project Team | 500 | MOOE
Conducting School-based DRRM Training/ Workshop | Conducted School Quarterly Emergency/ Disaster Drills | Monthly | School Heads/ SDRRM Project Team/ MVS Stakeholders | 2500 | MOOE/ PTA/ LGU
Conducting School Quarterly Emergency/ Disaster Drills | Conducted School Quarterly Emergency/ Disaster Drills | Monthly | BFP, PNP, RHU, LDRRM, SDRRM Project Team, Employees, and Students | 2000 | MOOE
Integrate DRR Education into the carrier subjects/ student organizations | Integrated DRR education in the lesson plan/ Sports/Scouting training designs | Monthly | School Heads/ SDRRM Project Team/ Teachers
Assessing the conducted activities | Communication Letters/ ACR/ Narrative Reports/ Evaluation Results | Monthly | School Heads/ SDRRM Project Team/ Teachers and Stakeholders | 500 | MOOE/ PTA
BERNLEY JOY M. NOBLEZA |  |  | AMOR ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## CPP
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Action - Reaction, Child-Protection
Problem Statement: Increased number of reported incidence of bullying in the classroom
Project Objective Statement: Eliminate incidence of bullying from 40% to 0 and promote Children's Rights in 2020
Root Cause: Cutting classes/Absenteeism
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parents | Sent Communication | June | Teachers, School Head, stakeholders | NC | MOOE
Organizing project team | Organized project team | June | Teachers, School Head, stakeholders | NC
Convening the class officers for an orientation meeting | Organized student protection policy | Year round | SSG Adviser and Student Leaders | 5000 | MOOE
Formulating a plan of activities on CPP to implement advocacy | Organized student protection policy | Year round | SSG Adviser and Student Leaders | 10000 | MOOE, LGU
Coordinating with the other organizations and offices if problem exist that violates the rights of children | Organized student protection policy | Year round | SSG Adviser and Student Leaders | 1000 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | Year round | CPP Chairman | NC
Prepared by:
RUBY ROSA F. SIPRADO |  |  | DIVINA B. SANCHEZ
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## ICF LAC SESSION
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: ICT LAC session
Problem Statement: 15 out of 53 teachers were not able to perform basic skills in word, excel and powerpoint application
Project Objective Statement: Increase number of teachers from 26 to 53 that were able to perform basic skills in word, excel powerpoint application
Root Cause: No prioritization in terms of attending ICT LAC Session
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Signing of Agreement between the teacher and ICT Coordinator regarding the schedule of session | Signed MOU | Computer Lab June-March | Teachers and ICT Coordinator
Prepare Training Design for ICT LAC Session | Training Design | June | ICT Coordinator | 500
Discussing and applying session will initiated regarding MS Application such as Word, Excel power point, etc. | Accessed computer by session | Computer Lab June-March | Teachers and ICT Coordinator
A session for registering and opening e-mail accounts and visiting other DepEd portals such as LRMDS, DepEd Websites, Searching in Google engine, etc. | Registered to DepEd portals and Websites | Computer Lab June-March | Teachers and ICT Coordinator | 2000 | DepEd DCP
Conducting Computer usage and net usage assessment | Assessed on computer usage and net usage | Computer Lab per quarter | Teachers and ICT Coordinator | 1000 | DepEd
Using of desktop computers to formulate communications | Facilitated the transfer of communication and various types electronically | Year round | School Head, Designate Head, Teachers, and Finance personnel | 2000 | MOOE
Acomplishing the ACR | Accomplished ACR with supported MOV's | Year round | ICT Coordinator, ICT Teacher | NC
Prepared by:
CAREN MAY C. NAPUTOL |  |  | ELVIRA P. GICA
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## i connected internet
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: I- connected
Problem Statement: No access of internet in the computer laboratory
Project Objective Statement: Provide internet connection from 0 to 1 in 2020
Root Cause: Insufficient of funds
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Conducting meeting to budget officer and School heads | Minutes of meeting | June | ICT coordinator, Budget officer and School heads | NC
Canvassing materials needed for Internet intallation | Canvassed materials | June | ICT coordinator, Budget officer and School heads | NC
Applying contract for Internet installation | Signed Contract | August | School Head, Supply officer | NC
Allocating Budget for Monthly payment for internet connection | APP | Whole year | School Head, Supply officer | 60000 | MOOE/ Donations
Liquadating Expenses | Liquadation | Whole year | School Head, Supply officer | 500 | MOOE
Prepared by:
CAREN MAY C. NAPUTOL |  |  | ELVIRA P. GICA
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## WASH WINS
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: SBM WiNs
Problem Statement: Irregular supply of potable water for drinking and hand washing
Project Objective Statement: Increase accessibility of potable water from 1 to 3 in 2020
Root Cause: No technical assistance provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 |  | NC
Repair or replace damaged faucet and fix leaked pipes | Checked and improved drinking water source and facilities | Aug-March 2019-2020 | Plumber and Physical Coordinator | 20000 | PTA Fund
Installing water tanks or purchase water purifier | Installed water tanks |  |  | 40000 | MOOE
Constructing new classroom CRs. | Constructed new classroom | Nov-March 2019-2020 | Skilled personnel | 100000 | MOOE/PTA Fund
Conducting lecture on Proper Sanitation and Hygiene to orient students | CRs and introduced learners “The proper Sanitation and Hygiene” | Year round | Teacher and students | 2000 | HRPTA/Fund
Providing trash bins with proper label | Disposed garbage properly | June-March 2019-2020 | Eco-Friendly coordinator and advisers | 6000 | Classroom Project/HRPTA Fund
Conducting deworming twice a year | Conducted bi-annual deworming to all students | Twice a year | Advisers, RHU, DepEd Nurses and students | 8000 | 4Ps Sponsorship
Examine student's dental conditions | Examined dental condition | Twice a year | RHU, DepEd Dentist | 20000 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman and Co- Chairman | NC
Prepared by:
ENRICO D. GASPAN |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## ECO FRIENDLY
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Sustainable Eco-friendly School Program
Problem Statement: Sustained Eco-friendly School Program
Project Objective Statement: Implement the Program on Sustainability of the Eco-friendly Environment from 50% to 100% in 2020
Root Cause: Technical assistance not provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Providing compost heap/ pit and campaigning for a proper segregation and disposal of wastes in school. | Implemented and incorporated programs on Eco- friendly in Science and TLE lessons | June 2019- April 2020 | Teachers | 3000 | Science Club Fund
Providing drainage and keeping the environment clean |  | June 2019- April 2020 | SSG Officers | 20000 | SSG, MOOE
Segregating garbage and putting it in compost heap/pit to decomposed into an organic material. | Implemented and incorporated programs on Eco- friendly in Science and TLE lessons | June 2019- April 2020 | SSG Officers | NC
Implementing the junk- food free in the school canteen. | Items in the school canteen are junk food free | June 2019- April 2020 | Canteen Manager, Vendors | NC
Implementing the '' BOTE MO - I SHOOT MO- MAGING PERA TO'' program | Generated income of the program | June 2019- April 2020 | Teachers, Students | NC
Implementing the 5 O’ clock habit (in the afternoon) “ The Picking up of Trashes around the school campus) | Maintained clean and green campus. | June 2019- April 2020 | Teachers, Students | NC
Collecting recyclable and salable bottles |  | June to April 2019 |  | 1000 | SSG
Eco friendly members with SSG Officers from eco- friendly motivated students and teachers |  | June 2019- April 2020 | Teachers, Students | NC
Organizing the materials stored in “Material Recovery Facility” | Organized MRF | 2017-06-01 | Science Teachers, PTA | NC
Assigning the Science Club to spearhead the tree planting activity. | Planted 200 hard wood trees in the school campus | June 2019- Sept. 2020 | Science Club Advisers, Students | 5000 | LGU
Coordinating with the community for an eco-friendly activities and projects | Coordinated eco-friendly activities with other community clubs | June to April 2019 | Teacher and students | NC
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Eco- friendly Chairman and co- chairman | NC
Prepared by:
CHRISTY ANGELIE M. BELECARIO |  |  | NIÑA ROSARIO RAÑOLA
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## CFSS
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Class – Away- School
Problem Statement: Achieve the 7 goals of the CFSS from grade 7 to 10
Project Objective Statement: Conduct 3 to 7 CFSS sessions in different barangay with Project BEST in 2020
Root Cause: Cutting classes/Absenteeism
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 |  | NC
Orienting teachers and students on the 7 goals of CFSS | Aimed at achieving 100% of the 7 goals of the CFSS | Year round | Advisers, Guidance Advocate | 1000 | MOOE
Accomplishing the checklist of activities to be conducted per item per goal in order to track the progress of becoming a CFS. | Accomplished the checklist | Year Round | SSG Adviser | 500 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | CFSS Chairman | NC
Note: Please record also the date of monitoring per project Please attach this form to the AIP template
Prepared by:
DIVINA B.SANHEZ |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## BRIGADA
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: BRIGADA ESKWELA IN BAYANIHAN SYSTEM
Problem Statement: 150 out of 750 students and parents hesitates to participate in Brigada Eskwela
Project Objective Statement: Increase participation of students and parents in Brigada Eskwelafrom 500 to 750 in 2020
Root Cause: Technical Assistance not provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 |  | NC
Establishing strong partnership thru meetings, assemblies and other school activities | Increased by 20% the stakeholders participation in school activities | Year round | Stakeholders, SH & Teachers | NC
Preparing program of work | Prepared program of work for brigada eskwela | January to April | Stakeholders, SH, Teachers & brigada coordinator | NC
Encouraging stakeholders to join the weeklong school maintenance prior to opening of classes | Sustained and maintained the best implementation of BRIGADA ESKWELA | Year round | SH, Teachers, Students Stake-holders
Doing work thru bayanihan system such as minor repair, cleaning the school classrooms, gardens and the entire campus, pruning trees, fixing chairs and seats etc. | Repaired and clean environment | Brigada Eskwela schedule | Parents, alumni, BHWs, BFP, Military men, LGU, Brgy Officials | 250000 | BE donors
Accepting cash or in kind donations and sign Certificate of Acceptance | Accepted in kind donation for the construction of covered walk | May | Alumni, SH, other civic spirited citizens | 100000 | PTA
Documenting the work before, during and after the BRIGADA ESKWELA | Sustained BRIGADA ESKWELA as Area Awardee | May | BRIGADA ESKWELA Documenter | 1000 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | After Brigada Eskwela schedule | BRIGADA ESKWELA Chairman | NC
Prepared by:
MARIA LOURDES R. CABUGOY |  |  | NIÑA ROSARIO RAÑOLA
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## GAD
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Reinforced Gender Equality in School
Problem Statement: Inequality distribution of Gender issue and Social responsibility
Project Objective Statement: Conduct orientation on Women’s Right from 0 to 6 in 2020
Root Cause: Gender Issue not given importance
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Attending Seminar/ Team building | Integrated of different subject in Gender And Development | October | Teachers, Principal, Guidance Counselor, Non-teaching Staff | 5000 | PTA/ MOOE
Institutionalizing celebration activities | Institutionalized GAD Activites | June- March | PTA, Teachers, Principal, Guidance counselor | 500
Discussing GAD lessons in all subjects | LP of GAD as part of the lessons | June to March | Teachers | NC
Celebrating Women’s month | Awareness on the rights and equality to develop potential habits. | February | Stake holder, teacher, PTA, Administration | 1000 | PTA/MOOE
Conducting Career guidance on choosing best career path | Conducted career guidance program | 2017-02-01 | Teacher, PTA, Guidance counsellor | 500 | PTA
Accomplishing activity completion report | Accomplished ACR | Year round | Guidance Counselor | 500 | MOOE
Prepared by:
RUBY ROSA F. SIPRADO |  |  | NIÑA ROSARIO RAÑOLA
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## SBM
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: School Based Management Level 3 Accreditation Program
Problem Statement: There 's a decrease of enrollment by 2.65% that greatly affects ACCESS which is 45% of the SBM accreditation criteria.
Project Objective Statement: Meet the SBM level 3 accreditation criteria from 70% to 100% in 2020
Root Cause: did not meet the cirteria
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | 2000 | MOOE
Organizing project team | Organized project team | June |  | 2000 | MOOE
Organizing four (4) committees and assign each team with one principle. | Achieved SBM-PASBE Level 3 Accreditation. | June 15- 30 | Head Designate, Teachers, SBM Coordinator | 2000 | MOOE
Updating and arranging artifacts and MOVs according to principle and levels. | Updated artifacts and MOV's | 2017-08-01 | SBM Coordinator and School Head | 15, 000 | MOOE
Conducting the D-O-D process and assess, analyze to get SBM Level of Practice | Conducted D-O-D | 2017-08-15 | SBM Coordinator and School Head | 5, 000 | MOOE
Note: Please record also the date of monitoring per project Please attach this form to the AIP template
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | SBM Chairman and Co- chairman | 10, 000 | MOOE
Prepared by:
JOEVEN A. GLORIA |  |  | CAREN MAY C. NAPUTOL
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## SMEA
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: School Monitoring, Evaluation and Adjustment
Problem Statement: 5 out of 53 teachers submitted delayed reports
Project Objective Statement: On time submission of reports by 50 out 53 teachers in 2020
Root Cause: Less technical assistance provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Organizing and orienting SMEA Team functions and responsibilities | Validated, Reported, & adjusted school M & E results and identified gains and gaps | Quarterly | SMEA Team | 500 | MOOE
Monitoring and gathering data of school programs and projects | Monitored and gathered data | Quarterly | SMEA Team | 500 | MOOE
Validating and adjusting results of school accomplishments | Validated and adjusted results | Quarterly | SMEA Team | 500 | MOOE
Organizing MOVs to support the data and its accomplishments | Discussed results and determine findings, suggestions and recommendations | Every 3rd week of the month per quarter | SMEA Team | 500 | MOOE
Analyzing the result and finding out the causes | Compared result of the representations thru graphs, and interpreted data | June to March | SMEA Team and Teachers | NC
Identifying the Issues and problems for RESOLUTION and identify the intervention to address the need | Reported SMEA data at the end of every quarter | Quarterly | EMIS Coordinator, IT Teacher, DepT Heads | NC
Accomplishing the ACR | Accomplished ACR with supported MOV's | June to March | SMEA Chairman | NC
Prepared by:
CAREN MAY C. NAPUTOL |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## REPAIR
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Repaired today, Damaged away
Problem Statement: Only 40% of repair and maintenance being accomplished by the school
Project Objective Statement: Increase accomplishment in school's repair and maintenance from 40% to 100% in 2020
Root Cause: Insufficient of funds
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 |  | NC
Providing column truss, tool room and roofing of temporary Automotive Shop | Provided roofing of temporary automotive shop for SHS | May-June 2019 | Carpenter | 100000 | MOOE/PTA
for SHS Repaint walls and roofs of administration building | Painted walling and roofing of administration buildings | 2017-07-01 | Physical Facilities Officer and skilled personnel | 30000 | MOOE
Preparing of program of work. | Repaired Auditorium | June to March 2019 | School head, | 100000 | LGU/PTA and MOOE
Seeking assistance for BUB fund |  | Quarterly | Physical development | 2000 | MOOE
Presenting the need to LGU for equity. |  | AUGUST 1 2019 | Officers, Budget officers | 25000 | MOOE
Repairing ceiling and roofing HE building | Repaired ceiling and roofing HE building | AUGUST 1 2019 | Physical Facilities Officer and skilled personnel | 10000 | MOOE/PTA
Constructing covered walk | Constructed covered walk | September-October, 2019 | SHS Teacher in welding, students and skilled personnel | 50000 | MOOE
Repiping for water system | Replaced small water supply pipes | 2017-07-01 | Supply officer and skilled personnel | 100, 000 | MOOE
Replacing damaged fluorescent bulb/lamp, circuit breaker, old electrical wirings | Replaced damage/busted electrical lines and new fluorescent bulbs/lamps, , circuit breaker, old electrical wirings | 2017-06-01 | Supply officer and skilled personnel | 150000 | MOOE
Repainting Basketball Court lines | Repainted basketball court lines | 2017-07-01 | Supply officer and skilled personnel | 2000 | MOOE
Maintaining laptop printers, projector and flash drive in good condition | Provided electrical facility in the computer laboratory | Year round | Electrician, Physical Facilities Coordinator | 5000 | MOOE
Maintaining computer tables, door and window grills for computer safe keeping | Maintained computer tables, door and window grills for computer safe keeping | 2017-06-01 | SH, Physical Facilities Coordinator | 1000 | MOOE/ Donations
Maintaining Electrical facilities- wirings, outlets, switch, circuit breaker etc. |  | 2017-06-01 | Electrician, Physical Facilities Coordinator | 5000
Installing air conditioning to provide ventilation for both students and computers | Installed air conditioning to provide ventilation for both students and computers | 2017-06-01 | Electrician, Physical Facilities Coordinator | 10000
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Repair and Maintenance Chairman | NC
Prepared by:
ELMER B. GARCIANO |  |  | IAN EINSTEIN O. DIGMAN
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## PARTNERSHIP AND LINKAGES
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: PARTNERSHIP AND LINKAGES
Problem Statement: MVS linkage with the stakeholders is not yet properly established
Project Objective Statement: Intensify linkage among stakeholders from 5 to 10 in 2020
Root Cause: Technical assistance not provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing data according to priority of importance. Adjust data of the SRC by quarter. Prepare AIP . | Organized data according to priority of importance. Adjust data of the SRC by quarter. Prepare AIP . | June - February | School Head | NC
Inviting parents and stakeholders thru a letter | Increased number & % of participation of parents | February | Teachers and SH | NC
Identifying organization to adopt a student for school support | No. of students in ASSP | Year round | Section Adviser and Guidance Counselor | 5000 | Stakeholders
Converging of stakeholders | MOA signed | Year round | SHS coordinator and Guidance Counselor | 500 | MOOE
a. Students' Development | 85% of the parents’ attendance were manifested in the conduct of the SOSA | February | School Head | NC
b. Physical Facilities | Sustained all programs that are beneficial to the students and the school as well. |  |  | NC
c. Teachers Development |  |  |  | NC
d. Status of Programs and Projects |  |  |  | NC
Categorizing the achievements of the school thru the AIP/SIP and those that have been the concern during the meeting | Categorized achievements of the school thru the AIP/SIP and those that have been the concern during the meeting | March | School Head | 2000 | PTA Fund
Delivering of SOSA | Delivered SOSA | July | School Head | NC
Presenting future plans of the School in the next 3 years. | Presented future plans of the School in the next 3 years. | June | School Head | 500 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Support and Linkage Chairman | NC
Prepared by:
DIVINA B. SANCHEZ |  |  | RUBY ROSA F. SIPRADO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## SENIOR HIGH SCHOOL
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Implementation of Senior High School under TVL
Problem Statement: 25% of facilities and equipment are available
Project Objective Statement: Provide adequate facilities and equipment for K-12 from 25% to 100% in 2020
Root Cause: Insufficient of funds
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Purchasing furnishings | Purchased supplies for SHS | 2017-06-01 | SHS coordinator, supply officer | 109000 | SHS Budget
Purchasing SHS supplies | Purchased supplies for SHS | 2017-06-01 | SHS coordinator, supply officer | 100000
Purchasing reference books | Purchased supplies for SHS | 2017-06-01 | SHS coordinator, supply officer | 10000
Budgeting for Year end expenses | Budgeted for Year end expenses | 2017-06-01 |  | 10000
Purchasing materials for Certificates and awards | Purchased materials for Certificates and awards | 2017-06-01 |  | 20000
Budgeting for Water supplies | Budgeted for Water supplies | Year round |  | 30000
Purchasing of Auto, SMAW and Beauty care supplies |  | 2017-06-01 |  | 57000
Sending letters to barangay chairman to disseminate information for SHS enrolment | Disseminated information for SHS Grade 12 | April-May 2016 | Linkage Chairman | 500 | MOOE
Conducting advocacy and early registration for grade 11 | Enrolled 163 students in grade 11 in the TVL track | January-March 2017 | Grade 10 teachers | 500 | MOOE
Displaying of streamers | Encouraged elementary graduates to enroll in a specific tech-voc track | MAY 14 2017 | SHS Coordinator | 1000 | MOOE
Acomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman and co- chairman | NC
Prepared by:
NESTOR A. CASTAÑOS Jr. |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## DRUMS AND LYRES
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Drum and Lyre Corps
Problem Statement: Inadequate number of instruments in Drum and Lyre Corps
Project Objective Statement: Increase the number of functional drums and lyres equipment from 5 to 10 in 2020
Root Cause: Lack of Technical Assistance
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Registering prospect DLC members | Registered prospect DLC members | All Year Round | Chairman and officers of DLC | 50 pesos/ student | Membership Funds
Purchasing of instruments |  | 2017-06-01 | DLC Chairman, supply officer | 15000 | PTA
Acomplishing the ACR | Accomplished ACR with supported MOV's | July - Dec. 2019-2020 | Project Chairman | NC
Note: Please record also the date of monitoring per project Please attach this form to the AIP template
Prepared by:
GRACELYN V. MOJADO |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## PROJECT WATCH
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Pro- Watch- Catch- Match
Problem Statement: Few teaching and non- teaching personnel are not reporting to work on time
Project Objective Statement: Promote punctuality among teachers and employees from 50 to 55 in 2020
Root Cause: No technical Assistance provided to all students and teachers.
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | June |  | NC
Discussing the importance of Project WATCH in a meeting | Attended flag ceremony daily-for teachers, every Monday for non-teaching | 2017-06-01 | All teaching and non-teaching personnel | 5000 | MOOE
Understanding the value of punctuality | Encouraged early attendance among teaching and non-teaching | Daily | All teaching and non-teaching personnel | NC
Upgrading biometrics to register time in and out of daily attendance correctly | Upgraded biometrics to register time in and out of daily attendance correctly | Monthly | Biometrics in-charge | NC
Checking of teachers and employees registry | Identified under time and absences of T & E | Every end of the month | Biometrics in-charge | NC
Accomplishing the ACR | Accomplished ACR with supported MOV's | Year round | Biometrics in-charge | NC
Prepared by:
IAN EINSTEIN O. DIGMAN |  |  | MARICHIE R. DONAYRE
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## MOOE UTILIZATION (2)
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: MOOE Utilization
Problem Statement: Only 70% of school utilities and supplies being catered of the MOOE fund
Project Objective Statement: The school utilities and supplies will be catered of the MOOE fund from 70% to 100% by 2020
Root Cause: Insufficient funds
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 | Teachers, School Head, stakeholders | NC
Prioritizing payments of the following: | Paid school utility bills | Year round | School head and supply officers |  | MOOE
a. monthly water bills |  |  |  | 195000
b. monthly electrical bills |  |  |  | 200000
c. monthly internet connection |  |  |  | 60000
Sending teachers to trainings | Sent teachers to trainings | Year round | School head | 300000 | MOOE
Allocating funds for travel expenses | Allocated funds for travel expenses | Year round | School Bookkeeper | 100000 | MOOE
Purchasing office supplies and materials | Purchased office supplies and materials | Year round | Supply Officer | 520000 | MOOE
Creating bidding awards committee | Created bidding awards committee | Year round | School head | NC
Preparing and submitting liquidated reports | Prepared and submitted liquidated reports | Year round | Supply Officer and Disbursing officer | NC
Prepared by:
MARICHIE R. DONAYRE |  |  | ELVIRA P. GICA
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## sir monthly report
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Monthly Accomplishment Report
Problem Statement: Made prepare monthly accomplishment report
Project Objective Statement: Prepare 10 monthly accomplishment report in one School year
Root Cause: Identify problems and provide alternative met every month.
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Monitor Schhool activities daily | Daily Checklist | 2017-06-01 | Principal | 1000 | MOOE
Supervise and observe classes | Supervisory plan, report and TCOR | 2017-06-01 | Principal | 1000 | MOOE
Implement school PAP's , liquadate MOOE | List of School PAP,s , MOOE Report | 2017-06-01 | Principal | 5000 | MOOE
Conduct school conferences | Note, minute, attendance pictorials | 2017-06-01 | Principal | 1000 | MOOE
Prepare and submit ORS and MAR every Month with identified problems/ solutions | ORS and MAR Report | 2017-06-01 | Principal | 1000 | MOOE
Prepared by:
FRANCISCO B, LATORRE
School Principal II

## MULTI MEDIA PROGRAM
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Multi- Media Program
Problem Statement: Multi-media not available for instruction
Project Objective Statement: Increase the number of functional LCD Projector for instruction through solicitations /donations from stakeholders from 2 to 5
Root Cause: Not prioritize
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 |  | NC
PTA prepare solicitation letter | Prepared communication | 2017-06-01 | Linkage coordinator | NC
Implement the project on the solicited amount | Implemented project | 2017-10-01 | Subject Teachers
Making teaching-learning strategy more effective to students thru multi-media presentations Ex. TV set/Projector | Increase level of participation of students in all learning areas thru provision of TV set per classroom | Yearly | School Head, Budget Officer | 25,000 (15,000) (5,000) (5,000) | PTA Donation other external stakeholder
Increase students participation in classroom activity using film viewing and DVD Presentation | Decreased students at risk of dropping Out | Daily | Teachers and Students | 2000 | MOOE
Acomplishing the ACR | Accomplished ACR with supported MOV's | Year round | Project Chairman | NC
Prepared by:
DIVINA B. SANCHEZ |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B, LATORRE
School Principal II

## aip review
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: LOVE ( Letting Others View and Empowered)
Problem Statement: 25% or 10 out of 39 programs and projects are not accomplished
Project Objective Statement: Increase the percentage of accomplishment of the programs and projects in E-SIP from 75% to 95% in 2019
Root Cause: less connection to the stakeholders
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating to the School Planning Team | Sent Communication | 2017-04-01 | School Head | NC
Review the E-SIP to determine the unaccomplished programs and projects | Reviewed SIP | 2017-04-01 | School Planning Team | 1000 | MOOE
Planning for the enhancement of the E-SIP | Enhanced E- SIP | 2017-04-01 | School Planning Team | 1000 | MOOE
Finalizing and presenting the E-SIP to the stakeholders | Finalized and Presented E-SIP | 2017-05-01 | School Head | 2000 | MOOE
Submitting the E-SIP to SDS for approval | Approved E-SIP | 2017-05-01 | School Head | 500 | MOOE
Implementing / accomplishing the programs and projects | Accomplished programs and projects | 2018-03-01 | Project Chairman and Co- chairman | 1000 | MOOE
Monitoring and Evaluating the E-SIP | Monitored and Evaluated E-SIP | 2018-05-01 | Project Chairman and Co- chairman | 1000 | MOOE
Accomplishing the ACR | Accomplished ACR | 2018-05-01 | Project Chairman and Co- chairman | 1000 | MOOE
Prepared by:
ELPEDIO P. MABIYA |  |  | DIVINA B. SANCHEZ
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## SCHOOL LAND TITLING
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: TAX DECLARATION PROGRAM
Problem Statement: No lot titling being acquired by the school
Project Objective Statement: Secure tax declaration of the school lot by 0 to 1 in 2020
Root Cause: Insufficient funds
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team | Sent Communication | 2017-06-01 | Teachers, School Head, stakeholders | NC
Organizing project team | Organized project team | 2017-06-01 |  | NC
Inquiring the documents necessary for school lot titling | Prepared documents | 2017-06-01 | Supply officer, School Head | NC
Budgeting t for the school titling | Prepared budget | 2017-06-01 | Supply officer, School Head | 10000 | MOOE
Requesting support from LGU and PTA | Sent Communication | 2017-07-01 | Linkage coordinator | NC
Acquiring tax declaration from the Assessor's office | Acquired tax declaration | 2017-10-01 | Supply officer, School Head | 2500 | MOOE
Preparing and submitting liquidated reports | Prepared and submitted liquidated reports | 2017-10-01 | Disbursing officer | NC
Prepared by:
MARICHIE R. DONAYRE |  |  | ELMER B. GARCIANO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B, LATORRE
School Principal II

## charm record mnageemnrt
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: CHARM ( Classroom for Harmony and Accurate Record Management)
Problem Statement: 5 out of 53 teachers are handling classes advisory section in temporary classrooms with satisfactory record management
Project Objective Statement: Reduce the number of teachers with satisfactory classroom and record management from 9 to 0 by 2020
Root Cause: shortage of classroom
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating Project team and School Planning team | Sent Communication | 2017-06-01 | School Heads, School Planning team and Project Team | NC
Organizing project team and School Planning team | Organized project team School Planning team | 2017-06-01 |  | 1000 | MOOE/ PTA
Planning for the schedule of classroom Evaluation and Record Management | Conducted Classroom and Record management Evaluation | Aug- Sept 2017 | School Heads. PTA and SGC | 1000 | MOOE/ PTA
Submitting reports regarding the Evaluation results | Submitted reports | 2017-09-01 | School Heads. PTA and SGC | 100 | MOOE
Waiting for the 24 classrooms to be finished | Newly contructed building | 2017-12-01 | School Heads, School Planning team | NC
Tranferring of teacher- adviser from grade 7- 10 to the newly constructed building | Room assignment Plan | 2017-12-01 | School Heads, School Planning team | NC
Accomplishing the ACR | Accomplished ACR | 2017-12-01 | Project Chairman and Co- chairman | NC | MOOE
Prepared by:
DIVINA B. SANCHEZ |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## help lesson plan ta
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: HELP ( Helping to Enhance Lesson Planning)
Problem Statement: 11 out of 53 teachers are delayed in submitting lesson plans
Project Objective Statement: Reduce the no. of teachers who are delayed in submitting lesson plans from 11 to 1 in 2020
Root Cause: Less of technical assistance provided
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating Project team | Sent Communication | 2017-06-01 | School Heads, Project Team | NC
Organizing project team | Organized project team School Planning team | 2017-06-01 |  | NC
Planning for the schedule of giving technical assistance | Planned schedule | 2017-06-01 | School Heads, Project Team | NC
Providing Technical assistance | Corrected lesson plan | whole year |  | NC
Accomplishing the ACR | Accomplished ACR | 2017-03-01 | Project Chairman and Co- chairman | 100 | MOOE
Prepared by:
ELPEDIO P. MABIYA |  |  | DIVINA B. SANCHEZ
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## PATHWAYS
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Pathways Construction
Problem Statement: 50% of the pathways are not constructed
Project Objective Statement: Construct pathways from 50% to 100% in 2020
Root Cause: not prioritized
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating to the Stakeholders | Sent Communication | 2017-06-01 | School Head | NC
Organizing project team | Organized project team | 2017-06-01 | School Head, Department Heads | 1000 | MOOE/ PTA
Making a resolution to construct pathways through the PTA | Formulated resolution | 2017-07-01 | PTA Officers | 300 | MOOE
Submitting resolution for approval in the higher office | Approved resolution | 2017-08-01 | School Head | 500 | MOOE
Constructing the pathways | Constructed pathways | 2017-05-01 | School Head | 100000 | Donations/ PTA
Monitoring and Evaluating of the pathways | Monitored and Evaluatedproject | 2018-05-01 | Project Chairman and Co- chairman | 1000 | MOOE
Accomplishing the ACR | Accomplished ACR | 2018-05-01 | Project Chairman and Co- chairman | 1000 | MOOE
Prepared by:
ELMER B. GARCIANO |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## sosa
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Statement of Shool Address
Problem Statement: 3 out of six SOSA held in different school assemblies in 2017
Project Objective Statement: Increase the number of SOSA held from 3 to 6 by 2020
Root Cause: overlapping of activities
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating Project team | Sent Communication | 2017-06-01 | School Heads, Project Team | NC
Organizing project team | Organized project team School Planning team | 2017-06-01 |  | NC
Planning for the schedule in conducting SOSA | Planned schedule | every quarter | School Heads, Project Team | NC
Communicating the PAPs coordinators and other stakeholders | Corrected lesson plan | every quarter |  | NC
Accomplishing the ACR | Accomplished ACR | 2017-03-01 | Project Chairman and Co- chairman | 100 | MOOE
Prepared by:
ELPEDIO P. MABIYA |  |  | DIVINA B. SANCHEZ
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## SAFETY AND SECURITY PROGRAM
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: Perimeter Fence
Problem Statement: 25% of the perimeter fence is not constructed
Project Objective Statement: Construct perimeter fence from 75% to 100% in 2020
Root Cause: not prioritized
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating to the Stakeholders | Sent Communication | 2017-06-01 | School Head | NC
Organizing project team | Organized project team | 2017-06-01 | School Head, Department Heads | 1000 | MOOE/ PTA
Making a resolution to construct a perimeter fence through the PTA | Formulated resolution | 2017-07-01 | PTA Officers | 300 | MOOE
Submitting resolution for approval in the higher office | Approved resolution | 2017-08-01 | School Head | 500 | MOOE
Constructing the Perimeter fence | Constructed Perimeter fence | 2017-05-01 | School Head | 500000 | Donations/ PTA
Monitoring and Evaluating of the PF | Monitored and Evaluated E-SIP | 2018-05-01 | Project Chairman and Co- chairman | 1000 | MOOE
Accomplishing the ACR | Accomplished ACR | 2018-05-01 | Project Chairman and Co- chairman | 1000 | MOOE
Prepared by:
ELMER B. GARCIANO |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
FRANCISCO B. LATORRE
School Principal II

## KURYENTE
ANNEX 9 Project Work Plan and Budget Matrix
Project Title: KURYENTE ATTENTION- GADGET PROTECTION
Problem Statement: 30% of the electrical lines need replacement and installation of transformer is necessary.
Project Objective Statement: Install additional transformer and replace 100% of the damage electrical lines in 2020
Root Cause: Inadequate school facility
Project Work Plan and Budget Matrix
Activity | Output | Date of Implementation | Person Responsible | Budget | Budget Source
Communicating project team and parent | Sent Communication | June | Teachers, School Head, stakeholders | NC |  | KURYENTE ATTENTION- GADGET PROTECTION
Organizing project team | Organized project team | June |  | NC
Requesting Leyeco assistance to assess school electrical facilities | Assessed electrical requirement of the school | June 15- 30 | School PDO and School Head | NC | NC
Applying for transformer pull out and testing | Tested calibrated transformer for installation | June 30- July 1-15, 2016 | School PDO | 1500 | MOOE
Installing additional school transformer | Installed additional school transformer | July 1-15, 2016 | School PDO | 100000 | MOOE
Replacing electrical lines | Replace additional electrical lines | July 1-15, 2016 | School PDO | 50000 | MOOE
Installing additional electric meter | Installed additional electric meter | July 1-15, 2016 | School PDO | 10000 | MOOE
Accomplishing the ACR | Accomplished ACR with supported MOV's | Year round | Project Chairman | NC
Prepared by:
JOSWELL B. GRANA |  |  | AMOR S. ZARCO
Project Chairman |  |  | Project Co-Chairman
Approved :
MANOLITA C. RUIZO
School Principal III

## ANNEX 2C
ANNEX 2C Student-led School Watching and Hazard Mapping
School Watching Checklist
/ | Broken window | / | Presence of stray animals inside the school campus
/ | Slippery pathway | / | Presence of electrical post/transformer near or within the school perimeter
/ | Blocked corridor | / | No system of release to parents during emergencies | /
/ | Heavy objects mounted on top of cabinets/shelves | / | No posted emergency hotlines around the school
/ | Flooded area | / | Garbage area (segregation of biodegradable and non-biodegradable)
/ | Busted plugs/light bulbs/electrical facilities |  | Detached or peeled off GI sheet
/ | Exposed electrical wires | / | Broken toilet bowl and/or sinks
| Protruding nails in chairs and tables | / | Broken chairs/desks/tables
/ | Broken door knobs | / | Blocked/no emergency exits
/ | Warning sign: Slippery pathways/corridors |  | Unmounted cabinets/shelves
| Plants mounted on the building railings |  | Medical kits in every classrooms
/ | Flooding | / | Bells/alarms
| Exposed chemicals and liquids | / | Condemnable building (i.e. very old structure, collapsing building and/or prominent cracks on classroom walls)
| Lack/absence of storage for equipment |  | Others (List as many as possible)
Unlabeled chemicals
/ | Dripping ceiling
/ | Open pit
/ | Stagnant water
/ | Unpruned trees/bushes/shrubs
Open/clogged canals
No ramps for elevated school buildings or other facilities
Swing-in doors

## annex 2a
ANNEX 2A Child-Friendly School Survey
GOAL #1: Encourage children’s participation in school and community
What your school should have or should be doing:
/ | Your school has a working student government.
/ | Your school involves students in meetings and planning sessions that concern their well-being.
/ | Your school involves students in the organizing, planning, and execution of the disaster preparedness and response plan.
/ | Your school encourages its students to get involved in community work.
/ | Your school has a mechanism or mechanisms – such as a school publication,
| 5 | Total number of action items checked for this goal
GOAL # 2: Enhance children’s health and well-being
What your school should have or should be doing:
/ | Your school maintains and regularly updates a health record of each pupil.
/ | Your school holds annual weighing and health examination of your pupils.
Your school holds annual dental examination of your pupils.
/ | Your school treats or refers pupils with health problems.
Your school treats pupils with decayed teeth.
/ | Your school has a feeding program for malnourished children.
/ | Your school serves or sells healthy and nutritious food in your premises.
/ | Your school practices proper waste disposal.
/ | Your school has a steady supply of clean and safe drinking water.
/ | Your school has separate toilet facilities for boys and girls consisting of urinals and lavatories that are regularly maintained and kept clean.
/ | Your school has a functional clinic.
| 8 | Total number of action items checked for this goal
GOAL # 3: Guarantee safe and protective spaces for children
What your school should have or should be doing:
/ | Your classrooms have proper ventilation and lighting and enough space for 45-50 pupils.
/ | Your classroom desks and other furniture are sized to the age of the pupils. In the case of shared desks, each pupil has enough space to do seatwork.
/ | Your classrooms’ layout and furniture allow pupils to interact and do group work.
/ | Your classrooms have a bulletin board or a corner that displays helpful learning materials such as posters, illustrations, newspaper and magazine clippings, and your pupils’ own works.
/ | Your classrooms, facilities, and premises are regularly maintained and kept clean.
Your school has safe facilities in place to address hazard threats (e.g. fire exits, fire extinguishers, appropriate electrial wirings).
/ | Your school has identified and prepared alternative learning spaces in cases of emergencies.
Your school has adequate emergency/first aid kits that are readily available.
/ | Your school conducts regular evacuation drills for earthquake, fire, flooding, or tsunami.
/ | Your school has a library for reading and for study.
/ | Your school has facilities and equipment for recreation and sports
/ | Your school has sufficient lawn space and vegetation.
/ | Your school has duly assigned personnel in charge of securing its premises, its properties, and those of its pupils and teachers.
/ | Your school coordinates with the barangay and local authorities to ensure the safety and protection of your pupils.
/ | Your school has a policy against discrimination with regard to gender, cultural origin, social status, religious belief, and others.
/ | Your school has a program for children with special needs.
/ | Your teachers use non-threatening styles of discipline.
| 15 | Total number of action items checked for this goal
GOAL # 4: Encourage enrollment and competition
What your school should have or should be doing:
/ | Your school has a master list of all school-age children in the community, whether enrolled or not.
/ | Your school regularly coordinates with the local barangay council to identify school-age children who are out of school, for the purpose of bringing them to school.
/ | Your school conducts campaigns to encourage parents to enroll their children.
/ | Your school has a system to regularly check on the attendance of its pupils and address problems concerning non-attendance.
| 4 | Total number of action items checked for this goal
GOAL # 5: Ensure children’s high academic achievement and success
What your school should have or should be doing:
/ | Your school has a clear vision/mission statement that is prominently displayed and adequately explained to all school personnel.
/ | The principal and teachers are familiar with child-centered and child-friendly principles.
Your school provides each student a complete set of textbooks.
/ | Teachers regularly prepare their lesson plans.
/ | Your school encourages and promotes cooperative and “hands-on” learning (“learning by doing”).
The principal has data on the school’s past three years performance in the division, regional or national tests for the purpose of improving its current year performance.
/ | Teachers regularly monitor and assess their pupils’ academic performance, with the view of improving their performance.
/ | The school provides students access to ADM, ALS, and/or other learning materials for their use during emergencies.
| 6 | Total number of action items checked for this goal
GOAL # 6: Raise teachers’ morale and motivation
What your school should have or should be doing:
/ | Teachers undergo continuing and advance professional training at least once a year.
/ | Teachers are regularly trained in new and effective teaching-learning strategies.
/ | Teachers have their own lounge and/or work area.
/ | Teachers are given annual medical check-up.
/ | The principal provides strong direction and leadership guided by a written supervisory plan.
/ | The principal regularly monitors teachers’ performance and provides needed support.
/ | Teachers support their co-teachers by sharing teaching techniques and experiences.
/ | Your school provides annual medical examination to your teachers and other staff.
| 8 | Total number of action items checked for this goal
GOAL # 7: Mobilize community support for education
What your school should have or should be doing:
/ | Your school has a Parent-Teacher Association (PTA) that has elected leaders, meets regularly, and has a written plan of action. |  | q
/ | Your school coordinates with barangay institutions to identify children who are physically or sexually abused or are made to do hard physical labor, for the purpose of identifying their special needs. |  | q
| Your school coordinates with the barangay and local institutions to enroll illiterate parents in literacy programs. |  | q
| Your school takes the lead in conducting literacy programs for illiterate parents. |  | q
/ | Your school enlists the support of community organizations to help raise funds and resources for learning. |  | q
/ | The principal regularly monitors teachers’ performance and provides needed support.Your school invites parents to discuss with your teachers the learning experiences and progress of their children. |  | q
/ | Your school consults parents in the drafting of its policies, and in the planning and implementation of school activities. |  | q
/ | Your school has organized and capacitated the School Disaster Risk Reduction and Management Committee (SDRRMC). |  | q
/ | Your school has strong partnerships with external stakeholders in order to address disaster risk reduction and the CCA-related needs of the school (i.e. data and statistics, capacity building, resources, etc). |  | q
| 7 | Total number of action items checked for this goal
Total number of action items checked for this goal.